## Charter
<Company>
Six Sigma Project Charter
Product or Process
Category(BB/GB)
Name of Belt | XYZ
Sponsor
Start Date
Opportunity for improvement
Short statement of the project delivearable (Problem to be solved) | Improve productivity by 10%
|  | Current | Target | Benchmark | Units
Objectives and measures (as applicable) | External Customer defects
Reduction in COPQ
DPMO/DPU/% defective
Cycle Time
Productivity
Sigma Level
Payback
Project Scope
Team Members
Schedule | Milestone | Date
Start
Measure Phase Completed
Analyze Phase Completed
Improve Phase Completed
Control Phase Completed
Approvals | Sponsor | MBB | Finance

## Project Scope
Project Scope
Please include a SIPOC Diagram or a flow chart showing scope of the project |  | Sample for reference
Castings from supplier
Receiving Inspection
Rough Machine
Finish Machine
Assemble
Inspect
Ship
Project Scope

## Project Tracker
Six Sigma Project Tracker
Project: |  | Improve productivity by 10% | [7 empty] | Belt: |  |  | Start Date: |  | 2006-08-01
|  | Week---------------------> | Tools | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Phase |  | Activity |  | 2006-08-08 | 2006-08-15 | 2006-08-22 | 2006-08-29 | 2006-09-05 | 2006-09-12 | 2006-09-19 | 2006-09-26 | 2006-10-03 | 2006-10-10 | 2006-10-17 | 2006-10-24 | 2006-10-31 | 2006-11-07 | 2006-11-14 | 2006-11-21 | 2006-11-28 | 2006-12-05 | 2006-12-12 | 2006-12-19 | 2006-12-26 | 2007-01-02 | 2007-01-09 | 2007-01-16 | 2007-01-23 | 2007-01-30
Define | 1 | Define Problem statement | Charter, Pareto Chart
| 2 | Charter preparation and approval | Charter with Scope, Financials
| 3 | High Level Process Map | Process Mapping, Value Stream Mapping, Flow Charts
| 4 | Plan and kick-off the project | Team Charter
Measure | 5 | Detailed Process Map to identify Xs | Detailed Process Map
| 6 | Develop Measurement Plan and MSA | MSA
| 7 | Collect Data on Ys and Xs | Correlation, Multi Vari, Graphical Tools
Analyze | 8 | Baseline Process Stability & Capability | Control Charts, Process Capability
| 9 | Identify vital few Xs | Correlation, Multi Vari, Regression
| 10 | Establish Improvement Targets
Improve | 11 | Design and Optimize Solutions | DOE, Other Improvements
| 12 | Analyze Costs and Benefits | Cost Benefit Analysis
| 13 | Implement Best Solution | Final Capability, DOE results
Control | 14 | Verify Implemented Solution | Final Capability, Measurement System Reanalysis
| 15 | Update Costs and Benefits
| 16 | Institutionalize and document | Control Plan, Work Instructios, Procedures, Poka Yoke
| 17 | Communicate and Replicate

## Top Level process Map
Process Map
(Top Level)
|  | Project: | Improve productivity by 10%
| KPIVs (Xs) | C/U | Process | KPOVs (Ys)
X1 |  |  | <Process Name> |  | Y1
X2 |  |  |  |  | Y2
X3 |  |  |  |  | Y3
X4
X5
X6
X7
X8
X9
X10

## Detailed Process Map
|  |  | Project: | Improve productivity by 10%
Step |  | KPIVs (Xs) | C/U | Process | KPOVs (Ys)
1 | x1 |  |  | <Process Name> |  | y1
| x2 |  |  |  |  | y2
| x3 |  |  |  |  | y3
x4
x5
x6
x7
x8
x9
x10
2 | x1 |  |  | <Process Name> |  | y1
| x2 |  |  |  |  | y2
| x3 |  |  |  |  | y3
x4
x5
x6
x7
x8
x9
x10

## Team Charter
Six Sigma Project Team Members
Project | Improve productivity by 10%
Belt: | XYZ
Sr.No. | Members | %Time
1
2
3
4
5
6