## PERT Beta Dist
ID | Activity | Pessimistic | Optimistic | Most Likely | Expected | ABDEFHIJ | ABDEFHIJ | ABDEFGIJ | ABDEFGIJ | ACEFGIJ | ACEFGIJ | ACEFHIJ | ACEFHIJ | Variance | SD | Dependence
A | Prepare Plan and get approval from municipal authority | 70 | 30 | 45 | 46.6667 |  | 46.6667 |  | 46.6667 |  | 46.6667 |  | 46.6667 | 44.4444
B | Get loan sanctioned | 10 | 4 | 6 | 6.3333 |  | 6.3333 |  | 6.3333 |  | 0 |  | 0 | 1 |  | A
C | Excavation for RCC | 16 | 6 | 10 | 10.3333 |  | 0 |  | 0 |  | 10.3333 |  | 10.3333 | 2.7778 |  | A
D | Procure steel and cement | 5 | 2 | 3 | 3.1667 |  | 3.1667 |  | 3.1667 |  | 0 |  | 0 | 0.25 |  | B
E | construct foundation and RCC | 95 | 40 | 60 | 62.5 |  | 62.5 |  | 62.5 |  | 62.5 |  | 62.5 | 84.0278 |  | C,D
F | Brickwork and plastering | 50 | 20 | 30 | 31.6667 |  | 31.6667 |  | 31.6667 |  | 31.6667 |  | 31.6667 | 25 |  | E
G | Flooring | 15 | 8 | 10 | 10.5 |  | 0 |  | 10.5 |  | 10.5 |  | 0 | 1.3611 |  | F
H | Electricals and plumbing | 28 | 10 | 15 | 16.3333 |  | 16.3333 |  | 0 |  | 0 |  | 16.3333 | 9 |  | F
I | Painting and finishing | 22 | 12 | 15 | 15.6667 |  | 15.6667 |  | 15.6667 |  | 15.6667 |  | 15.6667 | 2.7778 |  | G,H
J | Completion Certificate | 30 | 5 | 15 | 15.8333 |  | 15.8333 |  | 15.8333 |  | 15.8333 |  | 15.8333 | 17.3611 |  | I
| Mean |  |  |  | 199 |  | 198.1667 |  | 192.3333 |  | 193.1667 |  | 199 | 0 | 0
| SD | [11 empty] | 13.6158
221.3959
65

## PERT House
ID | Activity | Max | Min | Most Likely | Expected | Dependence | Average | SD | Actual | ID | A | B | C | D | E | F | G | H | I | J
A | Prepare Plan and get approval from municipal authority | 60 | 30 | 45 | 45 |  | 15 | 6.1237 | #NAME? | Activity | Prepare Plan and get approval from municipal authority | Get loan sanctioned | Excavation for RCC | Procure steel and cement | construct foundation and RCC | Brickwork and plastering | Flooring | Electricals and plumbing | Painting and finishing | Completion Certificate
B | Get loan sanctioned | 8 | 4 | 6 | 6 | A | 2 | 0.8165 | #NAME? | Max | 60 | 8 | 14 | 4 | 80 | 40 | 12 | 20 | 18 | 25
C | Excavation for RCC | 14 | 6 | 10 | 10 | A | 4 | 1.633 | #NAME? | Min | 30 | 4 | 6 | 2 | 40 | 20 | 8 | 10 | 12 | 5
D | Procure steel and cement | 4 | 2 | 3 | 3 | B | 1 | 0.40825 | #NAME? | Most Likely | 45 | 6 | 10 | 3 | 60 | 30 | 10 | 15 | 15 | 15
E | construct foundation and RCC | 80 | 40 | 60 | 60 | C,D | 20 | 8.165 | #NAME? | Expected | 45 | 6 | 10 | 3 | 60 | 30 | 10 | 15 | 15 | 15
F | Brickwork and plastering | 40 | 20 | 30 | 30 | E | 10 | 4.0825 | #NAME? | Dependence |  | A | A | B | C,D | E | F | F | G,H | I
G | Flooring | 12 | 8 | 10 | 10 | F | 2 | 0.8165 | #NAME? | a | 15 | 2 | 4 | 1 | 20 | 10 | 2 | 5 | 3 | 10
H | Electricals and plumbing | 20 | 10 | 15 | 15 | F | 5 | 2.0412 | #NAME? | SD | 6.1237 | 0.8165 | 1.633 | 0.40825 | 8.165 | 4.0825 | 0.8165 | 2.0412 | 1.2247 | 4.0825
I | Painting and finishing | 18 | 12 | 15 | 15 | G,H | 3 | 1.2247 | #NAME?
J | Completion Certificate | 25 | 5 | 15 | 15 | I | 10 | 4.0825 | #NAME?
| Mean |  |  |  | 190 |  |  | 12.0761 | #NAME?

## Ref
ID | Activity | Pessimistic | Optimistic | Most Likely | Expected | Dependence | a | SD
A | Prepare Plan and get approval from municipal authority | 60 | 30 | 45 | 45 |  | 15 | 6.1237
B | Get loan sanctioned | 8 | 4 | 6 | 6 | A | 2 | 0.8165
C | Excavation for RCC | 14 | 6 | 10 | 10 | A | 4 | 1.633
D | Procure steel and cement | 4 | 2 | 3 | 3 | B | 1 | 0.40825
E | construct foundation and RCC | 80 | 40 | 60 | 60 | C,D | 20 | 8.165
F | Brickwork and plastering | 40 | 20 | 30 | 30 | E | 10 | 4.0825
G | Flooring | 12 | 8 | 10 | 10 | F | 2 | 0.8165
H | Electricals and plumbing | 20 | 10 | 15 | 15 | F | 5 | 2.0412
I | Painting and finishing | 18 | 12 | 15 | 15 | G,H | 3 | 1.2247
J | Completion Certificate | 25 | 5 | 15 | 15 | I | 10 | 4.0825
| Mean |  |  |  | 190
65

## Sheet2
Mean | 187.3
SD | 12.12
Confidence Level | Duration
75 | 195.4748
90 | 202.8324
95 | 207.2356
99 | 215.4953

## Sheet3
A | B | C | D | E | F | G | H | I | J | A | B | C | D | E | F | G | H | I | J | Duration
47.9665 | 6.6295 | 9.8245 | 2.9542 | 45.8549 | 31.3996 | 10.0518 | 13.558 | 13.4525 | 14.1469 | 47 | 6 | 9 | 2 | 45 | 31 | 10 | 13 | 13 | 14 | 172
53.0625 | 5.2643 | 9.6311 | 3.3672 | 49.7289 | 24.1105 | 10.4111 | 18.6298 | 15.9667 | 9.9352 | 53 | 5 | 9 | 3 | 49 | 24 | 10 | 18 | 15 | 9 | 177
47.5995 | 6.6857 | 13.065 | 3.2553 | 46.1027 | 31.9479 | 10.1451 | 14.656 | 16.1718 | 12.0146 | 47 | 6 | 13 | 3 | 46 | 31 | 10 | 14 | 16 | 12 | 179
36.3559 | 7.6637 | 8.7098 | 2.8839 | 54.1434 | 25.453 | 10.7866 | 13.7536 | 15.9684 | 17.946 | 36 | 7 | 8 | 2 | 54 | 25 | 10 | 13 | 15 | 17 | 168
45.9628 | 5.1086 | 10.5106 | 3.9265 | 59.8009 | 36.3965 | 9.8182 | 16.952 | 16.5611 | 21.0762 | 45 | 5 | 10 | 3 | 59 | 36 | 9 | 16 | 16 | 21 | 203
44.1342 | 5.6628 | 8.7294 | 2.4882 | 62.0564 | 35.2949 | 10.5208 | 12.9379 | 15.9237 | 12.1158 | 44 | 5 | 8 | 2 | 62 | 35 | 10 | 12 | 15 | 12 | 188
45.5625 | 6.2435 | 11.0416 | 3.1892 | 63.499 | 28.0135 | 9.4773 | 13.2392 | 17.4557 | 12.7351 | 45 | 6 | 11 | 3 | 63 | 28 | 9 | 13 | 17 | 12 | 189
37.3897 | 6.5583 | 9.9137 | 3.3333 | 72.8627 | 38.0841 | 9.7219 | 16.4284 | 15.7869 | 12.0776 | 37 | 6 | 9 | 3 | 72 | 38 | 9 | 16 | 15 | 12 | 199
46.263 | 6.2667 | 11.4446 | 3.1272 | 52.4592 | 32.1519 | 9.9368 | 14.5581 | 14.2497 | 13.0153 | 46 | 6 | 11 | 3 | 52 | 32 | 9 | 14 | 14 | 13 | 182
35.293 | 5.995 | 8.6374 | 2.7113 | 60.3836 | 33.6183 | 10.3375 | 14.9265 | 13.8044 | 10.8638 | 35 | 5 | 8 | 2 | 60 | 33 | 10 | 14 | 13 | 10 | 173
54.2662 | 6.0246 | 9.2232 | 2.9216 | 61.8558 | 25.4948 | 9.8362 | 16.4913 | 16.4962 | 18.0902 | 54 | 6 | 9 | 2 | 61 | 25 | 9 | 16 | 16 | 18 | 199
46.7692 | 6.2532 | 9.1178 | 2.6435 | 61.553 | 29.3991 | 8.5651 | 14.8756 | 13.6972 | 10.1702 | 46 | 6 | 9 | 2 | 61 | 29 | 8 | 14 | 13 | 10 | 182
54.797 | 6.2152 | 9.7371 | 3.6475 | 62.3046 | 25.5218 | 11.4644 | 15.7124 | 13.5943 | 17.1959 | 54 | 6 | 9 | 3 | 62 | 25 | 11 | 15 | 13 | 17 | 195
44.7988 | 5.981 | 11.0628 | 3.0679 | 66.8492 | 32.879 | 11.4116 | 17.3181 | 16.6659 | 14.1712 | 44 | 5 | 11 | 3 | 66 | 32 | 11 | 17 | 16 | 14 | 200
42.3938 | 7.2536 | 11.3154 | 2.7892 | 52.4699 | 29.3083 | 9.0024 | 19.4625 | 14.7251 | 15.0699 | 42 | 7 | 11 | 2 | 52 | 29 | 9 | 19 | 14 | 15 | 182
46.0441 | 6.65 | 10.1854 | 2.9064 | 65.1367 | 28.7585 | 8.8824 | 17.3403 | 14.6397 | 18.6679 | 46 | 6 | 10 | 2 | 65 | 28 | 8 | 17 | 14 | 18 | 198
42.8242 | 5.1599 | 11.0779 | 3.3322 | 51.0437 | 34.168 | 11.5164 | 13.4606 | 13.3804 | 7.2166 | 42 | 5 | 11 | 3 | 51 | 34 | 11 | 13 | 13 | 7 | 171
46.3959 | 5.2484 | 13.0326 | 3.5373 | 57.8598 | 33.2313 | 9.7366 | 13.534 | 13.8258 | 17.3599 | 46 | 5 | 13 | 3 | 57 | 33 | 9 | 13 | 13 | 17 | 192
44.3034 | 6.4563 | 7.7057 | 3.0314 | 64.0543 | 29.2888 | 10.3201 | 15.9742 | 12.6558 | 11.4346 | 44 | 6 | 7 | 3 | 64 | 29 | 10 | 15 | 12 | 11 | 182
47.6793 | 5.3911 | 9.3575 | 3.0326 | 54.8815 | 28.0729 | 11.5719 | 17.0597 | 16.3999 | 15.942 | 47 | 5 | 9 | 3 | 54 | 28 | 11 | 17 | 16 | 15 | 186
42.4483 | 4.512 | 11.5996 | 2.6133 | 54.7853 | 21.3293 | 10.4531 | 13.3248 | 13.0956 | 9.8994 | 42 | 4 | 11 | 2 | 54 | 21 | 10 | 13 | 13 | 9 | 163
52.6956 | 6.9517 | 10.7847 | 2.6061 | 57.5036 | 32.9807 | 9.8579 | 17.0874 | 14.2487 | 15.403 | 52 | 6 | 10 | 2 | 57 | 32 | 9 | 17 | 14 | 15 | 197
38.1297 | 5.3251 | 10.8326 | 2.5256 | 54.8737 | 37.7381 | 11.1676 | 11.6151 | 13.0458 | 22.2435 | 38 | 5 | 10 | 2 | 54 | 37 | 11 | 11 | 13 | 22 | 185
47.0536 | 6.1335 | 10.3551 | 2.8532 | 64.5846 | 26.6914 | 10.162 | 16.2985 | 14.4287 | 16.0081 | 47 | 6 | 10 | 2 | 64 | 26 | 10 | 16 | 14 | 16 | 193
55.1098 | 4.9424 | 13.137 | 3.4272 | 66.3009 | 28.2876 | 10.2493 | 15.2086 | 16.4484 | 18.4648 | 55 | 4 | 13 | 3 | 66 | 28 | 10 | 15 | 16 | 18 | 211
53.8455 | 5.3518 | 6.976 | 2.4064 | 68.5497 | 33.162 | 10.6338 | 12.6108 | 13.7276 | 16.2116 | 53 | 5 | 6 | 2 | 68 | 33 | 10 | 12 | 13 | 16 | 201
55.5341 | 6.1044 | 8.8441 | 3.6332 | 73.3266 | 33.6294 | 11.0531 | 14.3348 | 13.8434 | 15.9174 | 55 | 6 | 8 | 3 | 73 | 33 | 11 | 14 | 13 | 15 | 211
53.375 | 7.5767 | 7.0343 | 2.4784 | 56.6086 | 27.4788 | 10.1514 | 15.5049 | 15.6418 | 13.5231 | 53 | 7 | 7 | 2 | 56 | 27 | 10 | 15 | 15 | 13 | 186
56.3088 | 7.492 | 11.2818 | 2.1338 | 66.4477 | 29.1122 | 9.6013 | 10.8396 | 15.1623 | 15.0887 | 56 | 7 | 11 | 2 | 66 | 29 | 9 | 10 | 15 | 15 | 202
34.9517 | 5.594 | 10.6558 | 3.3267 | 54.9282 | 26.2135 | 9.6661 | 17.067 | 16.906 | 19.4047 | 34 | 5 | 10 | 3 | 54 | 26 | 9 | 17 | 16 | 19 | 176
37.0946 | 5.4693 | 9.6373 | 2.5398 | 46.2981 | 31.7383 | 10.6184 | 15.4378 | 15.3656 | 16.7183 | 37 | 5 | 9 | 2 | 46 | 31 | 10 | 15 | 15 | 16 | 169
34.1966 | 7.094 | 12.1853 | 2.0451 | 52.1813 | 35.6707 | 11.4669 | 13.3093 | 14.8132 | 19.6633 | 34 | 7 | 12 | 2 | 52 | 35 | 11 | 13 | 14 | 19 | 179
42.7069 | 4.282 | 7.6061 | 3.4701 | 58.0498 | 32.0366 | 9.9794 | 12.8583 | 15.6748 | 21.2598 | 42 | 4 | 7 | 3 | 58 | 32 | 9 | 12 | 15 | 21 | 187
41.1913 | 6.0311 | 9.791 | 3.341 | 66.5197 | 22.9101 | 9.167 | 14.0284 | 15.1808 | 7.2589 | 41 | 6 | 9 | 3 | 66 | 22 | 9 | 14 | 15 | 7 | 174
52.4454 | 5.9942 | 7.8483 | 2.9712 | 45.8961 | 28.3701 | 9.247 | 11.0203 | 13.7672 | 14.8859 | 52 | 5 | 7 | 2 | 45 | 28 | 9 | 11 | 13 | 14 | 170
51.411 | 6.4787 | 9.5946 | 3.4992 | 60.1121 | 28.9178 | 8.9039 | 16.6522 | 15.983 | 14.1273 | 51 | 6 | 9 | 3 | 60 | 28 | 8 | 16 | 15 | 14 | 193
47.8981 | 7.4741 | 12.4854 | 2.963 | 52.4875 | 27.8828 | 9.6765 | 11.9634 | 15.0024 | 16.2613 | 47 | 7 | 12 | 2 | 52 | 27 | 9 | 11 | 15 | 16 | 180
49.4262 | 5.2698 | 11.8925 | 3.1796 | 60.1453 | 24.3426 | 11.7172 | 15.7598 | 14.3678 | 11.4675 | 49 | 5 | 11 | 3 | 60 | 24 | 11 | 15 | 14 | 11 | 184
46.2954 | 5.272 | 12.8103 | 3.0017 | 56.9964 | 29.1265 | 8.5192 | 11.2101 | 16.3294 | 22.522 | 46 | 5 | 12 | 3 | 56 | 29 | 8 | 11 | 16 | 22 | 192
43.1692 | 6.4711 | 10.62 | 2.6001 | 72.6588 | 28.6101 | 8.8347 | 12.2332 | 16.3998 | 21.6612 | 43 | 6 | 10 | 2 | 72 | 28 | 8 | 12 | 16 | 21 | 202
54.9057 | 6.5457 | 6.5095 | 2.8471 | 47.1187 | 21.1111 | 10.9878 | 12.7049 | 16.1919 | 24.0498 | 54 | 6 | 6 | 2 | 47 | 21 | 10 | 12 | 16 | 24 | 180
41.746 | 5.8059 | 10.2244 | 3.2305 | 53.9456 | 23.7161 | 8.3405 | 16.0326 | 15.0665 | 21.6984 | 41 | 5 | 10 | 3 | 53 | 23 | 8 | 16 | 15 | 21 | 179
38.7232 | 4.4671 | 9.4233 | 3.0172 | 55.7594 | 26.5985 | 10.6962 | 15.289 | 14.7426 | 16.0485 | 38 | 4 | 9 | 3 | 55 | 26 | 10 | 15 | 14 | 16 | 173
56.2931 | 5.0019 | 9.5405 | 3.7711 | 67.9761 | 34.9763 | 9.2175 | 17.6033 | 13.8303 | 21.7204 | 56 | 5 | 9 | 3 | 67 | 34 | 9 | 17 | 13 | 21 | 217
34.3702 | 5.1083 | 8.7124 | 2.5404 | 57.8259 | 29.3704 | 10.1834 | 15.7275 | 16.5401 | 16.5481 | 34 | 5 | 8 | 2 | 57 | 29 | 10 | 15 | 16 | 16 | 175
44.3495 | 6.9601 | 10.6605 | 3.1521 | 65.1391 | 32.9195 | 9.9239 | 13.86 | 15.5125 | 11.797 | 44 | 6 | 10 | 3 | 65 | 32 | 9 | 13 | 15 | 11 | 190
41.2986 | 5.9791 | 10.8037 | 3.1829 | 62.1221 | 29.2398 | 9.8466 | 15.2934 | 12.7113 | 13.7021 | 41 | 5 | 10 | 3 | 62 | 29 | 9 | 15 | 12 | 13 | 182
49.8238 | 4.4599 | 9.3821 | 3.5273 | 55.9188 | 31.9522 | 9.0809 | 14.8929 | 15.4142 | 21.7324 | 49 | 4 | 9 | 3 | 55 | 31 | 9 | 14 | 15 | 21 | 194
56.4326 | 6.0515 | 11.1507 | 3.155 | 64.6955 | 37.2678 | 11.1939 | 15.2983 | 13.3022 | 12.3762 | 56 | 6 | 11 | 3 | 64 | 37 | 11 | 15 | 13 | 12 | 208
39.8485 | 6.4351 | 9.4678 | 3.5056 | 69.5259 | 31.0401 | 9.5487 | 14.3107 | 17.0374 | 18.2695 | 39 | 6 | 9 | 3 | 69 | 31 | 9 | 14 | 17 | 18 | 197
49.601 | 7.7637 | 8.5807 | 2.7178 | 65.5112 | 30.7923 | 10.2569 | 14.753 | 16.0601 | 11.7881 | 49 | 7 | 8 | 2 | 65 | 30 | 10 | 14 | 16 | 11 | 193
57.3522 | 5.6276 | 9.8818 | 2.4972 | 53.4468 | 27.1043 | 9.7179 | 16.2966 | 13.7719 | 6.8432 | 57 | 5 | 9 | 2 | 53 | 27 | 9 | 16 | 13 | 6 | 181
44.9357 | 5.4692 | 9.6558 | 3.3207 | 73.1376 | 34.7879 | 11.6346 | 16.6513 | 14.0442 | 21.1177 | 44 | 5 | 9 | 3 | 73 | 34 | 11 | 16 | 14 | 21 | 211
45.31 | 6.4158 | 11.2176 | 3.5052 | 46.2085 | 29.382 | 10.7723 | 10.9254 | 13.5534 | 20.0016 | 45 | 6 | 11 | 3 | 46 | 29 | 10 | 10 | 13 | 20 | 174
45.0406 | 6.5383 | 12.2793 | 2.6376 | 49.6027 | 33.2204 | 8.881 | 12.8092 | 13.5366 | 15.6836 | 45 | 6 | 12 | 2 | 49 | 33 | 8 | 12 | 13 | 15 | 179
57.6576 | 4.8435 | 8.5791 | 3.3155 | 61.8185 | 27.5872 | 10.8319 | 14.1795 | 14.4679 | 14.9708 | 57 | 4 | 8 | 3 | 61 | 27 | 10 | 14 | 14 | 14 | 195
43.8529 | 5.6614 | 10.8797 | 2.868 | 53.8561 | 27.2234 | 8.9797 | 12.8144 | 15.5452 | 12.5018 | 43 | 5 | 10 | 2 | 53 | 27 | 8 | 12 | 15 | 12 | 172
46.7991 | 5.2621 | 12.1147 | 3.6686 | 49.8955 | 36.7524 | 9.2733 | 13.3645 | 13.5955 | 19.9176 | 46 | 5 | 12 | 3 | 49 | 36 | 9 | 13 | 13 | 19 | 188
36.1886 | 5.9763 | 7.6287 | 2.7438 | 69.5319 | 30.8207 | 9.9187 | 11.0569 | 14.2187 | 17.9422 | 36 | 5 | 7 | 2 | 69 | 30 | 9 | 11 | 14 | 17 | 184
43.5508 | 6.9623 | 9.9485 | 3.6603 | 58.9043 | 25.6204 | 11.2997 | 14.813 | 14.2843 | 11.132 | 43 | 6 | 9 | 3 | 58 | 25 | 11 | 14 | 14 | 11 | 174
46.3587 | 4.9291 | 8.3161 | 3.1186 | 55.1467 | 22.4375 | 10.5895 | 15.1446 | 14.436 | 14.8152 | 46 | 4 | 8 | 3 | 55 | 22 | 10 | 15 | 14 | 14 | 174
43.6279 | 6.0411 | 12.9263 | 2.3723 | 69.4553 | 29.4857 | 8.3528 | 18.7705 | 14.5095 | 13.3541 | 43 | 6 | 12 | 2 | 69 | 29 | 8 | 18 | 14 | 13 | 198
42.5199 | 4.9523 | 7.7696 | 2.7129 | 51.0446 | 35.6268 | 11.4233 | 14.7662 | 14.9486 | 13.6314 | 42 | 4 | 7 | 2 | 51 | 35 | 11 | 14 | 14 | 13 | 176
44.1528 | 4.6409 | 9.8718 | 2.7549 | 62.9862 | 33.4352 | 9.0669 | 15.9684 | 16.8049 | 20.6285 | 44 | 4 | 9 | 2 | 62 | 33 | 9 | 15 | 16 | 20 | 199
44.3698 | 5.2044 | 7.5178 | 2.7332 | 54.8627 | 32.9794 | 10.4595 | 15.1732 | 15.9887 | 13.5764 | 44 | 5 | 7 | 2 | 54 | 32 | 10 | 15 | 15 | 13 | 180
37.9628 | 6.1615 | 9.3479 | 3.2351 | 59.3131 | 34.656 | 8.6059 | 18.7243 | 13.7403 | 17.4893 | 37 | 6 | 9 | 3 | 59 | 34 | 8 | 18 | 13 | 17 | 187
47.8133 | 4.7984 | 9.6718 | 3.3698 | 71.4073 | 34.171 | 11.9545 | 14.5083 | 12.1452 | 14.0987 | 47 | 4 | 9 | 3 | 71 | 34 | 11 | 14 | 12 | 14 | 201
40.2361 | 7.1628 | 9.8252 | 3.1588 | 52.2375 | 23.6196 | 10.8187 | 16.4559 | 14.7225 | 8.9671 | 40 | 7 | 9 | 3 | 52 | 23 | 10 | 16 | 14 | 8 | 162
44.5939 | 5.6379 | 10.1157 | 2.5561 | 50.6743 | 38.2628 | 10.0846 | 12.7922 | 14.2668 | 14.4034 | 44 | 5 | 10 | 2 | 50 | 38 | 10 | 12 | 14 | 14 | 182
42.2973 | 5.2343 | 12.0312 | 3.0978 | 70.83 | 32.8324 | 10.7945 | 12.7817 | 14.9569 | 17.7076 | 42 | 5 | 12 | 3 | 70 | 32 | 10 | 12 | 14 | 17 | 199
43.2858 | 5.96 | 13.2472 | 3.0033 | 60.8733 | 31.5581 | 10.243 | 16.1461 | 16.9059 | 22.4472 | 43 | 5 | 13 | 3 | 60 | 31 | 10 | 16 | 16 | 22 | 201
49.0206 | 6.2547 | 10.4598 | 2.7859 | 49.3638 | 25.1075 | 8.8647 | 11.7609 | 14.0697 | 8.8837 | 49 | 6 | 10 | 2 | 49 | 25 | 8 | 11 | 14 | 8 | 166
36.7306 | 6.1934 | 12.3445 | 2.7034 | 61.192 | 37.3837 | 10.5104 | 13.3962 | 13.9608 | 12.622 | 36 | 6 | 12 | 2 | 61 | 37 | 10 | 13 | 13 | 12 | 184
38.5565 | 6.4769 | 8.6124 | 2.9384 | 74.4758 | 35.7771 | 8.3342 | 12.1768 | 16.3027 | 21.9868 | 38 | 6 | 8 | 2 | 74 | 35 | 8 | 12 | 16 | 21 | 204
56.4397 | 5.3074 | 9.7136 | 2.655 | 64.4767 | 31.9644 | 10.2886 | 15.8716 | 16.2628 | 16.8652 | 56 | 5 | 9 | 2 | 64 | 31 | 10 | 15 | 16 | 16 | 207
53.8049 | 4.4473 | 10.9186 | 3.5726 | 71.2965 | 34.9341 | 9.593 | 14.4626 | 16.6519 | 11.1219 | 53 | 4 | 10 | 3 | 71 | 34 | 9 | 14 | 16 | 11 | 209
51.2347 | 6.8499 | 6.6339 | 3.3283 | 60.771 | 32.7862 | 10.7966 | 12.0689 | 12.949 | 9.5574 | 51 | 6 | 6 | 3 | 60 | 32 | 10 | 12 | 12 | 9 | 182
52.3604 | 6.4294 | 9.2521 | 2.2863 | 53.2462 | 26.6257 | 10.6076 | 17.8616 | 16.9904 | 15.9012 | 52 | 6 | 9 | 2 | 53 | 26 | 10 | 17 | 16 | 15 | 188
42.1057 | 6.7952 | 9.5344 | 2.247 | 73.7502 | 23.7055 | 8.9457 | 15.7198 | 13.6058 | 21.685 | 42 | 6 | 9 | 2 | 73 | 23 | 8 | 15 | 13 | 21 | 196
54.0173 | 5.583 | 10.0026 | 3.4984 | 66.0451 | 27.3818 | 9.2627 | 14.0707 | 15.251 | 9.0971 | 54 | 5 | 10 | 3 | 66 | 27 | 9 | 14 | 15 | 9 | 195
44.9857 | 5.5608 | 9.2122 | 2.8307 | 57.8939 | 26.2041 | 10.9594 | 15.1422 | 14.8691 | 14.8054 | 44 | 5 | 9 | 2 | 57 | 26 | 10 | 15 | 14 | 14 | 179
43.2213 | 5.7492 | 9.4464 | 3.3688 | 76.3938 | 29.4383 | 10.1625 | 14.3316 | 15.1368 | 12.854 | 43 | 5 | 9 | 3 | 76 | 29 | 10 | 14 | 15 | 12 | 198
40.4664 | 5.9701 | 10.793 | 3.2407 | 60.9265 | 34.4105 | 8.6441 | 15.7963 | 17.6024 | 16.1351 | 40 | 5 | 10 | 3 | 60 | 34 | 8 | 15 | 17 | 16 | 192
36.9056 | 6.198 | 11.5826 | 2.4112 | 53.1601 | 37.0344 | 10.0167 | 11.0123 | 14.4099 | 10.0045 | 36 | 6 | 11 | 2 | 53 | 37 | 10 | 11 | 14 | 10 | 172
47.2931 | 5.1856 | 12.1033 | 2.5402 | 50.8809 | 24.5922 | 11.3115 | 13.7802 | 15.8604 | 15.8639 | 47 | 5 | 12 | 2 | 50 | 24 | 11 | 13 | 15 | 15 | 176
35.4755 | 6.6369 | 10.7762 | 2.9693 | 70.0006 | 34.1786 | 8.2908 | 15.6423 | 14.1313 | 16.0123 | 35 | 6 | 10 | 2 | 70 | 34 | 8 | 15 | 14 | 16 | 194
43.8874 | 7.0128 | 10.5436 | 3.6936 | 74.3676 | 31.0721 | 9.6423 | 16.1023 | 13.3759 | 14.1096 | 43 | 7 | 10 | 3 | 74 | 31 | 9 | 16 | 13 | 14 | 201
49.613 | 6.4291 | 10.0203 | 2.3833 | 59.3942 | 28.9539 | 10.9711 | 19.0623 | 15.0016 | 9.4152 | 49 | 6 | 10 | 2 | 59 | 28 | 10 | 19 | 15 | 9 | 189
41.5024 | 7.1761 | 11.8609 | 3.1102 | 69.6791 | 22.5632 | 10.0584 | 16.9567 | 15.4194 | 17.0769 | 41 | 7 | 11 | 3 | 69 | 22 | 10 | 16 | 15 | 17 | 191
38.3378 | 4.6401 | 10.2927 | 2.7 | 55.3215 | 29.8304 | 9.183 | 13.3686 | 14.924 | 13.6958 | 38 | 4 | 10 | 2 | 55 | 29 | 9 | 13 | 14 | 13 | 172
42.6644 | 7.6984 | 9.7057 | 3.3508 | 56.0766 | 28.9768 | 9.5765 | 18.9834 | 14.4927 | 17.7576 | 42 | 7 | 9 | 3 | 56 | 28 | 9 | 18 | 14 | 17 | 184
37.9869 | 5.3071 | 7.7388 | 3.271 | 74.2151 | 28.3741 | 10.7075 | 15.5688 | 13.1655 | 14.6539 | 37 | 5 | 7 | 3 | 74 | 28 | 10 | 15 | 13 | 14 | 188
51.1548 | 6.3118 | 7.826 | 3.4142 | 67.1112 | 26.8258 | 10.3027 | 15.5566 | 16.6766 | 7.6676 | 51 | 6 | 7 | 3 | 67 | 26 | 10 | 15 | 16 | 7 | 189
40.6738 | 7.4218 | 11.901 | 3.5121 | 70.9543 | 27.224 | 10.9551 | 13.1166 | 15.2762 | 20.3547 | 40 | 7 | 11 | 3 | 70 | 27 | 10 | 13 | 15 | 20 | 196
41.7851 | 6.5351 | 8.4309 | 2.8222 | 63.3903 | 32.0806 | 10.9288 | 10.3133 | 17.0098 | 6.0067 | 41 | 6 | 8 | 2 | 63 | 32 | 10 | 10 | 17 | 6 | 177
36.9682 | 5.9962 | 10.4909 | 3.0387 | 62.5705 | 28.3741 | 10.3954 | 17.6073 | 16.8683 | 17.4426 | 36 | 5 | 10 | 3 | 62 | 28 | 10 | 17 | 16 | 17 | 186
52.0316 | 7.8137 | 11.1069 | 3.1116 | 48.6519 | 28.4931 | 9.6579 | 16.6927 | 15.2078 | 17.2786 | 52 | 7 | 11 | 3 | 48 | 28 | 9 | 16 | 15 | 17 | 187
42.8267 | 5.6424 | 9.6651 | 3.1258 | 54.2796 | 36.6728 | 10.6069 | 11.9561 | 16.1094 | 16.5983 | 42 | 5 | 9 | 3 | 54 | 36 | 10 | 11 | 16 | 16 | 184
40.5721 | 6.2888 | 9.4792 | 3.1583 | 57.3105 | 37.9222 | 10.0759 | 13.8726 | 15.8407 | 17.4449 | 40 | 6 | 9 | 3 | 57 | 37 | 10 | 13 | 15 | 17 | 188
42.506 | 6.5635 | 11.3364 | 2.9142 | 70.6513 | 26.222 | 11.7382 | 15.287 | 14.7019 | 14.4493 | 42 | 6 | 11 | 2 | 70 | 26 | 11 | 15 | 14 | 14 | 192
46.8562 | 6.9418 | 12.6182 | 3.5067 | 62.2832 | 27.2023 | 8.6816 | 14.9685 | 15.0987 | 16.6734 | 46 | 6 | 12 | 3 | 62 | 27 | 8 | 14 | 15 | 16 | 192
51.9664 | 4.4583 | 10.6274 | 2.5668 | 56.6002 | 24.9739 | 10.8691 | 16.7772 | 14.7363 | 11.2017 | 51 | 4 | 10 | 2 | 56 | 24 | 10 | 16 | 14 | 11 | 182
41.26 | 6.134 | 9.39 | 3.5549 | 71.5657 | 36.7472 | 11.1295 | 18.2133 | 15.0176 | 11.5435 | 41 | 6 | 9 | 3 | 71 | 36 | 11 | 18 | 15 | 11 | 201
47.4591 | 6.0013 | 11.2566 | 2.8369 | 59.442 | 32.7165 | 10.6687 | 16.1299 | 14.9074 | 17.4541 | 47 | 6 | 11 | 2 | 59 | 32 | 10 | 16 | 14 | 17 | 196
49.2855 | 5.9607 | 7.7585 | 3.0166 | 69.432 | 35.0669 | 9.5175 | 13.5125 | 15.5287 | 14.2184 | 49 | 5 | 7 | 3 | 69 | 35 | 9 | 13 | 15 | 14 | 202
39.3646 | 6.3834 | 10.5988 | 2.6823 | 61.7874 | 25.7485 | 10.9002 | 16.1245 | 14.1317 | 13.9785 | 39 | 6 | 10 | 2 | 61 | 25 | 10 | 16 | 14 | 13 | 178
48.8534 | 6.6326 | 12.7522 | 2.8777 | 46.7526 | 28.8 | 8.995 | 15.4405 | 15.0074 | 14.6056 | 48 | 6 | 12 | 2 | 46 | 28 | 8 | 15 | 15 | 14 | 178
58.1607 | 5.3186 | 9.5408 | 3.6251 | 69.5562 | 33.8575 | 9.9494 | 17.1901 | 14.7713 | 15.2066 | 58 | 5 | 9 | 3 | 69 | 33 | 9 | 17 | 14 | 15 | 215
48.4443 | 5.0948 | 9.025 | 3.4387 | 61.0076 | 38.3497 | 10.455 | 14.3604 | 15.2574 | 17.3695 | 48 | 5 | 9 | 3 | 61 | 38 | 10 | 14 | 15 | 17 | 202
43.9982 | 7.1002 | 9.9909 | 2.6044 | 58.4986 | 24.9272 | 9.2082 | 18.3696 | 16.0001 | 14.5413 | 43 | 7 | 9 | 2 | 58 | 24 | 9 | 18 | 16 | 14 | 182
46.6168 | 6.5778 | 9.064 | 3.4131 | 48.8394 | 27.5871 | 11.7431 | 13.4324 | 13.7506 | 22.2473 | 46 | 6 | 9 | 3 | 48 | 27 | 11 | 13 | 13 | 22 | 178
39.5682 | 6.0587 | 9.3384 | 2.9661 | 57.7142 | 35.5756 | 10.7065 | 14.9238 | 14.8328 | 19.784 | 39 | 6 | 9 | 2 | 57 | 35 | 10 | 14 | 14 | 19 | 187
46.7899 | 5.6819 | 7.9706 | 3.0117 | 62.926 | 28.8837 | 10.2905 | 17.0323 | 15.3392 | 12.5966 | 46 | 5 | 7 | 3 | 62 | 28 | 10 | 17 | 15 | 12 | 187
48.3503 | 6.1301 | 10.0185 | 3.4246 | 72.3143 | 28.2813 | 9.8169 | 15.7981 | 14.7106 | 15.1287 | 48 | 6 | 10 | 3 | 72 | 28 | 9 | 15 | 14 | 15 | 202
46.7843 | 5.2483 | 7.7806 | 2.9292 | 67.5916 | 34.1423 | 9.8827 | 17.8005 | 16.5688 | 17.2035 | 46 | 5 | 7 | 2 | 67 | 34 | 9 | 17 | 16 | 17 | 204
45.8346 | 5.2731 | 12.9091 | 2.6303 | 55.0507 | 26.7427 | 11.0631 | 13.6191 | 15.3466 | 12.2375 | 45 | 5 | 12 | 2 | 55 | 26 | 11 | 13 | 15 | 12 | 178
51.5363 | 6.4397 | 10.3764 | 3.0359 | 65.6728 | 31.4942 | 10.87 | 13.7258 | 15.6033 | 11.4425 | 51 | 6 | 10 | 3 | 65 | 31 | 10 | 13 | 15 | 11 | 196
52.7636 | 6.4352 | 12.7322 | 3.6981 | 60.7985 | 30.0298 | 10.5734 | 14.4816 | 13.7987 | 12.0768 | 52 | 6 | 12 | 3 | 60 | 30 | 10 | 14 | 13 | 12 | 193
46.2078 | 7.0231 | 11.6321 | 2.7827 | 54.18 | 39.081 | 8.8073 | 10.8678 | 15.4361 | 10.1452 | 46 | 7 | 11 | 2 | 54 | 39 | 8 | 10 | 15 | 10 | 185
40.5536 | 4.4001 | 12.1635 | 3.1818 | 50.3363 | 26.2337 | 9.7434 | 16.7847 | 16.2474 | 13.9802 | 40 | 4 | 12 | 3 | 50 | 26 | 9 | 16 | 16 | 13 | 173
48.852 | 6.4862 | 13.3781 | 2.6667 | 62.1548 | 26.3849 | 11.6477 | 14.2505 | 14.3676 | 7.8274 | 48 | 6 | 13 | 2 | 62 | 26 | 11 | 14 | 14 | 7 | 184
47.7781 | 5.8311 | 9.1615 | 2.6679 | 70.1636 | 31.2503 | 9.8754 | 13.5848 | 15.0711 | 14.6944 | 47 | 5 | 9 | 2 | 70 | 31 | 9 | 13 | 15 | 14 | 199
33.0555 | 5.9452 | 8.3209 | 2.4961 | 64.4546 | 23.0288 | 10.2082 | 17.2228 | 15.8783 | 15.8255 | 33 | 5 | 8 | 2 | 64 | 23 | 10 | 17 | 15 | 15 | 175
45.0567 | 6.2347 | 8.4259 | 3.0271 | 67.4479 | 36.8553 | 10.123 | 17.9092 | 16.9197 | 8.8926 | 45 | 6 | 8 | 3 | 67 | 36 | 10 | 17 | 16 | 8 | 197
54.4625 | 5.8881 | 10.6132 | 2.8291 | 68.5667 | 27.6752 | 9.6383 | 13.901 | 15.911 | 15.7571 | 54 | 5 | 10 | 2 | 68 | 27 | 9 | 13 | 15 | 15 | 202
46.0904 | 6.7758 | 8.9794 | 2.5403 | 64.1738 | 34.7299 | 9.9495 | 13.8334 | 14.2541 | 9.0933 | 46 | 6 | 8 | 2 | 64 | 34 | 9 | 13 | 14 | 9 | 188
42.7212 | 5.9257 | 7.658 | 3.8949 | 71.5272 | 23.3628 | 10.0992 | 16.7852 | 16.4789 | 13.5981 | 42 | 5 | 7 | 3 | 71 | 23 | 10 | 16 | 16 | 13 | 188
42.6966 | 5.2635 | 12.4143 | 2.7665 | 50.8011 | 21.9282 | 9.6696 | 13.6972 | 12.8084 | 12.775 | 42 | 5 | 12 | 2 | 50 | 21 | 9 | 13 | 12 | 12 | 162
50.8964 | 6.9727 | 9.1774 | 2.6607 | 60.0733 | 32.4501 | 10.9242 | 13.1344 | 15.0046 | 17.6251 | 50 | 6 | 9 | 2 | 60 | 32 | 10 | 13 | 15 | 17 | 196
52.1134 | 5.3643 | 10.6476 | 3.138 | 64.5089 | 27.538 | 10.7622 | 16.4918 | 14.5277 | 13.2304 | 52 | 5 | 10 | 3 | 64 | 27 | 10 | 16 | 14 | 13 | 196
35.166 | 6.6336 | 12.1752 | 2.4395 | 42.1254 | 32.4035 | 10.091 | 16.0997 | 15.111 | 17.404 | 35 | 6 | 12 | 2 | 42 | 32 | 10 | 16 | 15 | 17 | 169
39.3869 | 7.4329 | 10.6361 | 3.5882 | 58.084 | 28.9553 | 9.4279 | 15.3871 | 12.6905 | 24.1889 | 39 | 7 | 10 | 3 | 58 | 28 | 9 | 15 | 12 | 24 | 186
33.6579 | 5.8578 | 7.5395 | 2.8669 | 49.985 | 26.1564 | 10.8695 | 15.9094 | 15.0677 | 11.7115 | 33 | 5 | 7 | 2 | 49 | 26 | 10 | 15 | 15 | 11 | 156
40.5749 | 6.1129 | 9.2029 | 2.4869 | 60.7283 | 24.4838 | 9.1725 | 15.5559 | 13.0784 | 13.0851 | 40 | 6 | 9 | 2 | 60 | 24 | 9 | 15 | 13 | 13 | 174
42.8056 | 6.3053 | 10.3656 | 3.652 | 61.9481 | 29.4256 | 9.3943 | 15.8906 | 15.2868 | 16.3697 | 42 | 6 | 10 | 3 | 61 | 29 | 9 | 15 | 15 | 16 | 188
41.7218 | 7.0954 | 10.1827 | 3.2149 | 46.1378 | 24.7874 | 11.8981 | 18.385 | 15.3985 | 10.6159 | 41 | 7 | 10 | 3 | 46 | 24 | 11 | 18 | 15 | 10 | 164
51.2944 | 5.9744 | 8.435 | 3.6477 | 63.692 | 31.736 | 9.9275 | 15.156 | 13.0079 | 22.4714 | 51 | 5 | 8 | 3 | 63 | 31 | 9 | 15 | 13 | 22 | 203
45.1918 | 6.4247 | 8.4586 | 2.5141 | 63.6253 | 29.0742 | 10.6018 | 17.7676 | 16.9244 | 18.5208 | 45 | 6 | 8 | 2 | 63 | 29 | 10 | 17 | 16 | 18 | 196
40.1393 | 4.3448 | 9.034 | 2.9728 | 64.2726 | 28.6852 | 10.0804 | 14.5535 | 14.7871 | 21.2872 | 40 | 4 | 9 | 2 | 64 | 28 | 10 | 14 | 14 | 21 | 190
34.2176 | 6.8149 | 11.1306 | 3.0132 | 57.6096 | 21.8034 | 10.7907 | 19.0845 | 14.826 | 19.6242 | 34 | 6 | 11 | 3 | 57 | 21 | 10 | 19 | 14 | 19 | 175
49.1453 | 5.6596 | 10.2784 | 2.981 | 59.0963 | 27.6054 | 11.0266 | 14.339 | 14.7175 | 10.3177 | 49 | 5 | 10 | 2 | 59 | 27 | 11 | 14 | 14 | 10 | 183
48.3343 | 5.7214 | 11.2798 | 2.9202 | 59.6695 | 25.4735 | 8.4865 | 19.228 | 15.6416 | 17.0483 | 48 | 5 | 11 | 2 | 59 | 25 | 8 | 19 | 15 | 17 | 194
39.0902 | 7.3208 | 7.5413 | 2.8448 | 54.739 | 29.4307 | 10.6047 | 17.3332 | 13.6168 | 22.971 | 39 | 7 | 7 | 2 | 54 | 29 | 10 | 17 | 13 | 22 | 181
52.777 | 6.1246 | 12.4347 | 2.8652 | 63.7508 | 33.6585 | 10.0838 | 13.6184 | 14.6775 | 16.2741 | 52 | 6 | 12 | 2 | 63 | 33 | 10 | 13 | 14 | 16 | 203
37.9941 | 5.6332 | 12.163 | 3.6078 | 71.0403 | 24.4638 | 9.5394 | 15.572 | 13.0806 | 10.0418 | 37 | 5 | 12 | 3 | 71 | 24 | 9 | 15 | 13 | 10 | 182
37.591 | 5.8899 | 9.2197 | 2.3206 | 56.6401 | 21.6287 | 8.8613 | 10.8377 | 16.4249 | 13.4842 | 37 | 5 | 9 | 2 | 56 | 21 | 8 | 10 | 16 | 13 | 162
50.7682 | 6.7989 | 12.2535 | 2.968 | 61.2854 | 30.5067 | 9.1384 | 17.8981 | 16.5692 | 10.2171 | 50 | 6 | 12 | 2 | 61 | 30 | 9 | 17 | 16 | 10 | 196
47.1677 | 5.7719 | 9.0159 | 2.9189 | 46.9489 | 21.3028 | 9.2399 | 17.4489 | 15.656 | 10.6542 | 47 | 5 | 9 | 2 | 46 | 21 | 9 | 17 | 15 | 10 | 165
44.6313 | 7.2987 | 7.74 | 2.7512 | 50.4534 | 34.5043 | 10.1838 | 17.8256 | 16.7655 | 14.1211 | 44 | 7 | 7 | 2 | 50 | 34 | 10 | 17 | 16 | 14 | 182
50.5327 | 6.2137 | 7.9481 | 3.1892 | 62.6438 | 30.8512 | 9.6458 | 15.776 | 14.7505 | 6.3649 | 50 | 6 | 7 | 3 | 62 | 30 | 9 | 15 | 14 | 6 | 184
53.3669 | 6.6111 | 9.0582 | 3.0333 | 63.9353 | 31.3407 | 9.5264 | 11.7618 | 15.1499 | 11.0662 | 53 | 6 | 9 | 3 | 63 | 31 | 9 | 11 | 15 | 11 | 193
55.3006 | 5.2719 | 7.4799 | 3.0509 | 45.0411 | 31.7934 | 10.9564 | 16.8652 | 16.1366 | 18.3372 | 55 | 5 | 7 | 3 | 45 | 31 | 10 | 16 | 16 | 18 | 188
43.8349 | 6.3856 | 11.1733 | 3.3369 | 54.6113 | 29.8043 | 9.4242 | 13.3051 | 15.0067 | 17.4243 | 43 | 6 | 11 | 3 | 54 | 29 | 9 | 13 | 15 | 17 | 182
53.9487 | 6.279 | 10.0573 | 3.3437 | 61.0115 | 26.8654 | 10.5457 | 13.7516 | 13.7304 | 19.6426 | 53 | 6 | 10 | 3 | 61 | 26 | 10 | 13 | 13 | 19 | 195
33.2352 | 5.4251 | 10.441 | 2.667 | 55.2886 | 34.1112 | 10.5616 | 15.4632 | 12.5446 | 10.2361 | 33 | 5 | 10 | 2 | 55 | 34 | 10 | 15 | 12 | 10 | 169
45.3074 | 4.8088 | 6.6533 | 3.3487 | 55.9363 | 28.0901 | 10.6086 | 12.7028 | 15.1901 | 16.8427 | 45 | 4 | 6 | 3 | 55 | 28 | 10 | 12 | 15 | 16 | 177
47.0045 | 5.3245 | 10.3247 | 2.9502 | 55.4972 | 29.7215 | 9.9205 | 12.8099 | 14.9686 | 10.6267 | 47 | 5 | 10 | 2 | 55 | 29 | 9 | 12 | 14 | 10 | 177
43.6892 | 4.6385 | 10.2844 | 2.4121 | 59.5033 | 28.9462 | 9.8977 | 17.099 | 14.202 | 15.6066 | 43 | 4 | 10 | 2 | 59 | 28 | 9 | 17 | 14 | 15 | 186
43.8978 | 5.8657 | 9.4738 | 2.668 | 60.9502 | 29.9362 | 8.7324 | 17.5183 | 14.4921 | 7.5843 | 43 | 5 | 9 | 2 | 60 | 29 | 8 | 17 | 14 | 7 | 179
46.5038 | 5.0191 | 11.9103 | 3.1298 | 48.7051 | 28.2607 | 11.0779 | 17.345 | 14.2711 | 13.9107 | 46 | 5 | 11 | 3 | 48 | 28 | 11 | 17 | 14 | 13 | 177
40.5447 | 5.6215 | 7.4518 | 3.1375 | 57.8539 | 26.8669 | 9.825 | 14.9668 | 15.0561 | 13.5839 | 40 | 5 | 7 | 3 | 57 | 26 | 9 | 14 | 15 | 13 | 172
47.8987 | 6.3686 | 9.0733 | 3.858 | 45.857 | 33.5573 | 11.3351 | 13.9108 | 17.2088 | 15.6515 | 47 | 6 | 9 | 3 | 45 | 33 | 11 | 13 | 17 | 15 | 179
47.2359 | 4.8667 | 10.757 | 2.8281 | 76.218 | 31.0367 | 8.8919 | 17.0676 | 15.5507 | 7.6185 | 47 | 4 | 10 | 2 | 76 | 31 | 8 | 17 | 15 | 7 | 203
47.5481 | 5.3683 | 8.6418 | 3.1418 | 54.2501 | 36.8145 | 8.7083 | 16.3979 | 16.4463 | 15.1581 | 47 | 5 | 8 | 3 | 54 | 36 | 8 | 16 | 16 | 15 | 192
47.2262 | 7.2674 | 9.461 | 2.7864 | 61.6089 | 33.3621 | 9.7081 | 15.8094 | 15.428 | 13.1043 | 47 | 7 | 9 | 2 | 61 | 33 | 9 | 15 | 15 | 13 | 193
44.4686 | 5.7699 | 9.9904 | 3.2596 | 59.262 | 32.0876 | 9.54 | 13.5442 | 16.0269 | 19.4986 | 44 | 5 | 9 | 3 | 59 | 32 | 9 | 13 | 16 | 19 | 192
45.7037 | 7.5199 | 9.0544 | 2.9735 | 61.2069 | 26.5229 | 10.9443 | 13.8144 | 16.6581 | 9.6452 | 45 | 7 | 9 | 2 | 61 | 26 | 10 | 13 | 16 | 9 | 179
45.9886 | 7.3669 | 10.4689 | 2.816 | 65.2229 | 36.378 | 10.8209 | 16.0742 | 16.5729 | 16.3597 | 45 | 7 | 10 | 2 | 65 | 36 | 10 | 16 | 16 | 16 | 204
54.3837 | 5.5971 | 12.2312 | 3.5203 | 46.9366 | 30.4234 | 9.2644 | 18.5887 | 14.5233 | 22.3532 | 54 | 5 | 12 | 3 | 46 | 30 | 9 | 18 | 14 | 22 | 196
45.2175 | 7.0339 | 12.0349 | 2.7884 | 70.1017 | 34.4622 | 9.618 | 16.0273 | 15.2403 | 14.0693 | 45 | 7 | 12 | 2 | 70 | 34 | 9 | 16 | 15 | 14 | 206
49.6813 | 5.6569 | 9.4791 | 2.705 | 47.3825 | 23.9881 | 11.1641 | 12.2191 | 15.4725 | 23.6329 | 49 | 5 | 9 | 2 | 47 | 23 | 11 | 12 | 15 | 23 | 178
33.9587 | 6.3905 | 12.8513 | 2.5765 | 54.2289 | 35.2139 | 9.1618 | 14.582 | 16.2503 | 15.9458 | 33 | 6 | 12 | 2 | 54 | 35 | 9 | 14 | 16 | 15 | 179
47.0858 | 7.6998 | 8.1741 | 3.2382 | 47.5473 | 29.8197 | 9.1139 | 18.5033 | 15.5299 | 12.9827 | 47 | 7 | 8 | 3 | 47 | 29 | 9 | 18 | 15 | 12 | 176
39.2717 | 7.3253 | 11.329 | 2.7508 | 66.0008 | 28.7172 | 10.0125 | 18.9688 | 16.7381 | 7.5333 | 39 | 7 | 11 | 2 | 66 | 28 | 10 | 18 | 16 | 7 | 185
41.9977 | 5.7279 | 7.6466 | 2.8767 | 62.4165 | 28.8674 | 9.0115 | 18.1543 | 15.3244 | 15.3124 | 41 | 5 | 7 | 2 | 62 | 28 | 9 | 18 | 15 | 15 | 186
47.8733 | 6.3074 | 8.7623 | 3.5218 | 57.634 | 26.2429 | 10.2865 | 15.6113 | 16.2219 | 18.7097 | 47 | 6 | 8 | 3 | 57 | 26 | 10 | 15 | 16 | 18 | 187
31.644 | 7.4752 | 9.4914 | 2.9935 | 67.3572 | 29.171 | 10.0909 | 12.0729 | 15.0114 | 17.2022 | 31 | 7 | 9 | 2 | 67 | 29 | 10 | 12 | 15 | 17 | 180
43.4794 | 6.1432 | 8.539 | 3.0651 | 56.2484 | 28.5721 | 9.8053 | 15.5782 | 15.1315 | 8.7763 | 43 | 6 | 8 | 3 | 56 | 28 | 9 | 15 | 15 | 8 | 173
48.5189 | 4.6859 | 10.8929 | 2.5968 | 74.9859 | 32.47 | 9.3331 | 14.4275 | 15.2417 | 6.9597 | 48 | 4 | 10 | 2 | 74 | 32 | 9 | 14 | 15 | 6 | 199
47.1859 | 7.0554 | 9.0872 | 3.286 | 47.5704 | 27.4407 | 10.5607 | 15.7868 | 14.5033 | 10.5748 | 47 | 7 | 9 | 3 | 47 | 27 | 10 | 15 | 14 | 10 | 169
52.8131 | 7.6421 | 6.3652 | 2.9165 | 57.0922 | 31.845 | 10.0143 | 17.0382 | 15.2235 | 7.6189 | 52 | 7 | 6 | 2 | 57 | 31 | 10 | 17 | 15 | 7 | 185
50.1012 | 6.3671 | 9.0248 | 2.6702 | 56.9997 | 30.3088 | 10.5419 | 19.2069 | 15.232 | 11.4972 | 50 | 6 | 9 | 2 | 56 | 30 | 10 | 19 | 15 | 11 | 190
57.841 | 7.0932 | 9.6748 | 2.578 | 59.5608 | 21.8517 | 10.6647 | 15.1152 | 17.0387 | 21.9571 | 57 | 7 | 9 | 2 | 59 | 21 | 10 | 15 | 17 | 21 | 199
44.9436 | 4.8845 | 6.8225 | 3.2792 | 75.6651 | 29.3329 | 9.0893 | 13.7515 | 13.0613 | 11.4581 | 44 | 4 | 6 | 3 | 75 | 29 | 9 | 13 | 13 | 11 | 191
53.8704 | 4.9234 | 13.0655 | 3.0195 | 59.6723 | 29.8815 | 10.7386 | 13.9696 | 15.6153 | 13.2224 | 53 | 4 | 13 | 3 | 59 | 29 | 10 | 13 | 15 | 13 | 195
32.2175 | 6.2695 | 6.991 | 2.9679 | 55.1488 | 31.665 | 9.2232 | 15.3052 | 15.4039 | 16.9499 | 32 | 6 | 6 | 2 | 55 | 31 | 9 | 15 | 15 | 16 | 170
34.3528 | 5.9085 | 10.398 | 2.7277 | 51.7676 | 36.5204 | 9.7544 | 17.7095 | 16.7146 | 12.9669 | 34 | 5 | 10 | 2 | 51 | 36 | 9 | 17 | 16 | 12 | 176
46.1983 | 7.4293 | 13.59 | 3.0868 | 71.6167 | 29.792 | 9.2592 | 16.9215 | 14.3106 | 19.9137 | 46 | 7 | 13 | 3 | 71 | 29 | 9 | 16 | 14 | 19 | 208
44.252 | 5.9422 | 10.0357 | 3.4426 | 51.6115 | 30.3341 | 10.9518 | 16.0376 | 13.1216 | 5.8494 | 44 | 5 | 10 | 3 | 51 | 30 | 10 | 16 | 13 | 5 | 169
45.342 | 5.8135 | 13.4156 | 2.4491 | 70.2451 | 28.4911 | 8.4167 | 12.9494 | 15.7695 | 7.7067 | 45 | 5 | 13 | 2 | 70 | 28 | 8 | 12 | 15 | 7 | 190
44.675 | 6.5347 | 9.5652 | 3.1228 | 52.4671 | 32.5401 | 10.6324 | 14.674 | 17.3832 | 14.4482 | 44 | 6 | 9 | 3 | 52 | 32 | 10 | 14 | 17 | 14 | 182
45.6591 | 6.3184 | 9.8887 | 2.4443 | 61.8403 | 27.1232 | 8.7856 | 13.6794 | 13.8089 | 11.8722 | 45 | 6 | 9 | 2 | 61 | 27 | 8 | 13 | 13 | 11 | 179
52.8754 | 5.7828 | 8.7913 | 3.3415 | 61.1426 | 24.5439 | 10.3427 | 13.5654 | 15.5107 | 21.4684 | 52 | 5 | 8 | 3 | 61 | 24 | 10 | 13 | 15 | 21 | 194
34.8605 | 6.8936 | 9.9087 | 2.5468 | 52.2584 | 33.7693 | 9.942 | 12.1877 | 15.1867 | 9.7487 | 34 | 6 | 9 | 2 | 52 | 33 | 9 | 12 | 15 | 9 | 164
44.9065 | 5.2008 | 8.5199 | 2.8731 | 53.4204 | 27.0512 | 10.0402 | 13.8345 | 13.4168 | 10.7414 | 44 | 5 | 8 | 2 | 53 | 27 | 10 | 13 | 13 | 10 | 168
52.7658 | 6.7175 | 10.0178 | 3.0088 | 49.1207 | 30.2624 | 10.4399 | 18.3345 | 14.1719 | 15.2206 | 52 | 6 | 10 | 3 | 49 | 30 | 10 | 18 | 14 | 15 | 188
32.3923 | 6.2521 | 13.0029 | 3.1511 | 64.106 | 29.5308 | 10.1988 | 15.8114 | 13.8988 | 16.8472 | 32 | 6 | 13 | 3 | 64 | 29 | 10 | 15 | 13 | 16 | 182
53.3479 | 5.4371 | 9.7006 | 2.9945 | 59.8509 | 31.6914 | 11.3591 | 12.3449 | 16.4689 | 12.6373 | 53 | 5 | 9 | 2 | 59 | 31 | 11 | 12 | 16 | 12 | 192
34.5469 | 4.5151 | 11.2827 | 2.6646 | 67.0246 | 27.9271 | 9.9417 | 14.0714 | 13.2365 | 14.4619 | 34 | 4 | 11 | 2 | 67 | 27 | 9 | 14 | 13 | 14 | 180
58.6452 | 6.6738 | 7.7928 | 3.1138 | 49.7057 | 31.3017 | 8.964 | 13.419 | 14.4863 | 15.0788 | 58 | 6 | 7 | 3 | 49 | 31 | 8 | 13 | 14 | 15 | 187
48.0632 | 4.6266 | 10.1321 | 3.2622 | 47.9255 | 32.3848 | 8.9545 | 15.976 | 14.5213 | 15.478 | 48 | 4 | 10 | 3 | 47 | 32 | 8 | 15 | 14 | 15 | 181
36.8652 | 5.4768 | 11.5088 | 2.8218 | 64.717 | 23.8789 | 10.5217 | 14.8707 | 13.6344 | 21.9485 | 36 | 5 | 11 | 2 | 64 | 23 | 10 | 14 | 13 | 21 | 182
45.704 | 6.1824 | 11.8002 | 2.7211 | 49.9992 | 27.0119 | 8.3776 | 16.5387 | 14.3493 | 14.2525 | 45 | 6 | 11 | 2 | 49 | 27 | 8 | 16 | 14 | 14 | 176
43.0813 | 5.4207 | 10.5033 | 3.758 | 64.9086 | 24.567 | 10.6064 | 19.3793 | 13.5341 | 12.2035 | 43 | 5 | 10 | 3 | 64 | 24 | 10 | 19 | 13 | 12 | 185
45.4213 | 6.3196 | 10.6523 | 3.0698 | 57.3905 | 23.3239 | 11.4943 | 16.1298 | 14.6253 | 15.8456 | 45 | 6 | 10 | 3 | 57 | 23 | 11 | 16 | 14 | 15 | 180
45.8653 | 6.0348 | 8.5532 | 2.642 | 64.493 | 25.2052 | 9.3342 | 14.3882 | 15.8636 | 19.5774 | 45 | 6 | 8 | 2 | 64 | 25 | 9 | 14 | 15 | 19 | 190
49.6281 | 6.4777 | 10.1214 | 3.5266 | 59.0152 | 31.7673 | 9.9872 | 13.4697 | 15.0334 | 16.4749 | 49 | 6 | 10 | 3 | 59 | 31 | 9 | 13 | 15 | 16 | 193
45.0584 | 5.9138 | 10.354 | 2.2394 | 68.1949 | 27.0193 | 10.1072 | 13.1557 | 15.2076 | 15.1212 | 45 | 5 | 10 | 2 | 68 | 27 | 10 | 13 | 15 | 15 | 193
51.0124 | 4.7783 | 9.8259 | 3.6508 | 42.7156 | 35.7098 | 9.3645 | 15.2762 | 14.9214 | 20.0789 | 51 | 4 | 9 | 3 | 42 | 35 | 9 | 15 | 14 | 20 | 186
36.6894 | 7.502 | 12.2975 | 2.8294 | 52.9242 | 21.3373 | 9.4776 | 16.2075 | 13.2685 | 9.5402 | 36 | 7 | 12 | 2 | 52 | 21 | 9 | 16 | 13 | 9 | 159
42.9775 | 4.7959 | 11.1114 | 2.7479 | 46.899 | 29.8413 | 10.1185 | 13.9708 | 14.1692 | 7.522 | 42 | 4 | 11 | 2 | 46 | 29 | 10 | 13 | 14 | 7 | 162
41.3982 | 4.9648 | 11.3436 | 2.883 | 50.4374 | 38.5037 | 9.657 | 16.2708 | 13.9864 | 11.9493 | 41 | 4 | 11 | 2 | 50 | 38 | 9 | 16 | 13 | 11 | 180
48.1733 | 5.7171 | 11.6904 | 2.9067 | 58.3131 | 28.3719 | 9.8078 | 12.3883 | 15.6441 | 15.8578 | 48 | 5 | 11 | 2 | 58 | 28 | 9 | 12 | 15 | 15 | 187
49.9155 | 5.3031 | 12.9388 | 3.2831 | 62.3991 | 21.403 | 11.3387 | 17.141 | 13.9696 | 20.4051 | 49 | 5 | 12 | 3 | 62 | 21 | 11 | 17 | 13 | 20 | 194
54.0892 | 4.4141 | 8.7701 | 2.4299 | 71.1009 | 21.6532 | 9.6095 | 13.9444 | 13.911 | 12.9236 | 54 | 4 | 8 | 2 | 71 | 21 | 9 | 13 | 13 | 12 | 192
55.3726 | 6.3654 | 9.5126 | 2.8275 | 55.3949 | 31.0657 | 10.0091 | 18.2107 | 14.8411 | 14.0395 | 55 | 6 | 9 | 2 | 55 | 31 | 10 | 18 | 14 | 14 | 196
46.7887 | 6.3035 | 9.3327 | 3.055 | 60.35 | 30.6333 | 9.3434 | 17.1762 | 13.7461 | 15.7013 | 46 | 6 | 9 | 3 | 60 | 30 | 9 | 17 | 13 | 15 | 190
42.96 | 6.3602 | 8.0622 | 3.5426 | 62.6393 | 22.256 | 8.7915 | 14.2958 | 16.8958 | 21.8008 | 42 | 6 | 8 | 3 | 62 | 22 | 8 | 14 | 16 | 21 | 185
46.101 | 4.8718 | 8.6662 | 3.5395 | 51.089 | 30.5859 | 8.5062 | 13.9057 | 14.862 | 10.7111 | 46 | 4 | 8 | 3 | 51 | 30 | 8 | 13 | 14 | 10 | 172
47.5257 | 5.8307 | 13.1671 | 2.8006 | 65.5584 | 25.9549 | 10.8668 | 12.1916 | 16.1119 | 12.5532 | 47 | 5 | 13 | 2 | 65 | 25 | 10 | 12 | 16 | 12 | 190
46.8478 | 6.3295 | 8.8295 | 2.7031 | 55.3346 | 35.5121 | 9.6018 | 12.3097 | 15.6816 | 13.2543 | 46 | 6 | 8 | 2 | 55 | 35 | 9 | 12 | 15 | 13 | 184
51.4862 | 6.4549 | 9.3332 | 2.9399 | 64.1866 | 36.7988 | 9.9968 | 10.9556 | 15.202 | 12.1932 | 51 | 6 | 9 | 2 | 64 | 36 | 9 | 10 | 15 | 12 | 197
57.5113 | 6.5103 | 11.8925 | 3.0179 | 60.4364 | 32.3022 | 10.7833 | 16.3805 | 16.5429 | 11.3014 | 57 | 6 | 11 | 3 | 60 | 32 | 10 | 16 | 16 | 11 | 203
43.1357 | 5.0377 | 11.8632 | 2.9784 | 58.8826 | 38.7353 | 10.4827 | 15.7543 | 16.778 | 10.1348 | 43 | 5 | 11 | 2 | 58 | 38 | 10 | 15 | 16 | 10 | 191
48.7193 | 6.6282 | 9.1709 | 2.4153 | 60.7994 | 30.4378 | 8.9595 | 15.26 | 17.1945 | 14.1562 | 48 | 6 | 9 | 2 | 60 | 30 | 8 | 15 | 17 | 14 | 193
40.6453 | 5.2987 | 12.0886 | 2.4909 | 44.4803 | 24.4544 | 9.7809 | 12.3615 | 14.9843 | 17.6136 | 40 | 5 | 12 | 2 | 44 | 24 | 9 | 12 | 14 | 17 | 163
34.5965 | 6.4376 | 6.666 | 3.0093 | 74.0688 | 35.874 | 8.6846 | 12.174 | 17.0028 | 16.4366 | 34 | 6 | 6 | 3 | 74 | 35 | 8 | 12 | 17 | 16 | 194
36.3966 | 6.66 | 13.296 | 3.1092 | 61.225 | 28.4254 | 10.2754 | 15.5741 | 14.0268 | 16.438 | 36 | 6 | 13 | 3 | 61 | 28 | 10 | 15 | 14 | 16 | 183
34.9322 | 4.8608 | 9.4902 | 2.9565 | 73.2171 | 31.1563 | 9.993 | 18.3933 | 15.6838 | 15.4803 | 34 | 4 | 9 | 2 | 73 | 31 | 9 | 18 | 15 | 15 | 195
52.8076 | 5.9818 | 12.6873 | 3.4905 | 55.4953 | 33.6258 | 10.43 | 14.1374 | 17.2652 | 10.3503 | 52 | 5 | 12 | 3 | 55 | 33 | 10 | 14 | 17 | 10 | 193
45.4813 | 4.9924 | 7.5373 | 3.5275 | 60.0023 | 31.241 | 9.6572 | 18.768 | 17.6394 | 11.879 | 45 | 4 | 7 | 3 | 60 | 31 | 9 | 18 | 17 | 11 | 189
46.5513 | 5.1245 | 10.1842 | 2.2847 | 66.4883 | 32.7042 | 9.8091 | 14.7607 | 16.5529 | 19.844 | 46 | 5 | 10 | 2 | 66 | 32 | 9 | 14 | 16 | 19 | 203
39.3965 | 4.4394 | 11.5148 | 2.8928 | 57.8448 | 39.7441 | 9.4947 | 17.536 | 13.2645 | 18.3038 | 39 | 4 | 11 | 2 | 57 | 39 | 9 | 17 | 13 | 18 | 194
39.7251 | 6.1951 | 11.1554 | 3.5399 | 72.9833 | 34.5469 | 8.9427 | 11.6779 | 17.2497 | 11.5136 | 39 | 6 | 11 | 3 | 72 | 34 | 8 | 11 | 17 | 11 | 195
37.3239 | 7.4572 | 8.164 | 2.8835 | 53.2537 | 35.1931 | 9.9852 | 17.4521 | 15.1695 | 13.0176 | 37 | 7 | 8 | 2 | 53 | 35 | 9 | 17 | 15 | 13 | 178
48.5464 | 7.1236 | 11.3489 | 2.301 | 57.5267 | 22.2273 | 9.4479 | 13.1795 | 13.2688 | 15.5999 | 48 | 7 | 11 | 2 | 57 | 22 | 9 | 13 | 13 | 15 | 179
39.5837 | 7.0892 | 10.3309 | 2.841 | 76.1259 | 31.5271 | 9.8581 | 14.5877 | 15.0616 | 15.9628 | 39 | 7 | 10 | 2 | 76 | 31 | 9 | 14 | 15 | 15 | 200
49.0809 | 6.3685 | 13.3384 | 3.1575 | 72.1244 | 32.8132 | 10.4747 | 14.9387 | 15.0044 | 13.0507 | 49 | 6 | 13 | 3 | 72 | 32 | 10 | 14 | 15 | 13 | 208
48.3716 | 7.3005 | 11.8486 | 2.2749 | 60.2151 | 22.0222 | 9.1592 | 15.8931 | 13.8094 | 23.2413 | 48 | 7 | 11 | 2 | 60 | 22 | 9 | 15 | 13 | 23 | 192
55.4358 | 6.4428 | 10.1355 | 2.6494 | 48.1583 | 35.212 | 11.1973 | 14.0696 | 13.6652 | 18.5246 | 55 | 6 | 10 | 2 | 48 | 35 | 11 | 14 | 13 | 18 | 193
36.3126 | 6.2521 | 8.7852 | 2.6355 | 54.8883 | 28.4776 | 10.1605 | 13.8385 | 12.8398 | 20.4997 | 36 | 6 | 8 | 2 | 54 | 28 | 10 | 13 | 12 | 20 | 171
49.3628 | 5.3952 | 11.6971 | 3.0577 | 47.2958 | 23.5583 | 9.4432 | 18.5324 | 14.679 | 15.5352 | 49 | 5 | 11 | 3 | 47 | 23 | 9 | 18 | 14 | 15 | 177
41.7399 | 5.8362 | 11.0121 | 3.2581 | 61.6899 | 28.2463 | 11.2217 | 14.7753 | 17.2052 | 19.1062 | 41 | 5 | 11 | 3 | 61 | 28 | 11 | 14 | 17 | 19 | 191
50.8155 | 6.5613 | 9.3584 | 2.3277 | 59.2108 | 21.2699 | 10.5722 | 15.9741 | 12.6674 | 16.6296 | 50 | 6 | 9 | 2 | 59 | 21 | 10 | 15 | 12 | 16 | 182
36.0155 | 6.8217 | 9.329 | 2.8799 | 65.1765 | 36.7252 | 11.2013 | 13.2442 | 15.4854 | 8.2933 | 36 | 6 | 9 | 2 | 65 | 36 | 11 | 13 | 15 | 8 | 182
58.9398 | 5.3209 | 12.0787 | 3.0355 | 56.2444 | 28.4136 | 9.3147 | 11.801 | 14.146 | 13.9371 | 58 | 5 | 12 | 3 | 56 | 28 | 9 | 11 | 14 | 13 | 192
49.3133 | 5.2705 | 10.3972 | 2.6144 | 72.3899 | 29.0094 | 10.4449 | 16.0714 | 15.171 | 17.3021 | 49 | 5 | 10 | 2 | 72 | 29 | 10 | 16 | 15 | 17 | 208
52.9345 | 4.6379 | 11.5531 | 3.0921 | 60.3377 | 25.6777 | 9.1153 | 17.2434 | 15.3085 | 16.7929 | 52 | 4 | 11 | 3 | 60 | 25 | 9 | 17 | 15 | 16 | 196
54.4904 | 5.5539 | 9.0507 | 2.6943 | 69.6908 | 27.8703 | 10.477 | 15.9844 | 16.6198 | 11.7372 | 54 | 5 | 9 | 2 | 69 | 27 | 10 | 15 | 16 | 11 | 201
48.0411 | 6.0817 | 6.2394 | 2.3951 | 63.5397 | 34.0852 | 9.0002 | 14.1015 | 16.5302 | 17.5705 | 48 | 6 | 6 | 2 | 63 | 34 | 9 | 14 | 16 | 17 | 198
57.393 | 5.1308 | 9.9738 | 2.863 | 67.869 | 22.5603 | 10.0978 | 15.2193 | 16.439 | 7.8456 | 57 | 5 | 9 | 2 | 67 | 22 | 10 | 15 | 16 | 7 | 193
53.831 | 5.5153 | 10.3855 | 3.3722 | 66.3139 | 25.133 | 10.462 | 15.4672 | 16.1248 | 18.9082 | 53 | 5 | 10 | 3 | 66 | 25 | 10 | 15 | 16 | 18 | 203
53.4127 | 7.2887 | 9.7059 | 2.9904 | 58.1314 | 33.6453 | 9.5902 | 18.5544 | 15.9924 | 21.1927 | 53 | 7 | 9 | 2 | 58 | 33 | 9 | 18 | 15 | 21 | 207
36.911 | 7.7307 | 9.2897 | 3.7818 | 52.7605 | 32.8263 | 10.1091 | 12.5334 | 15.4548 | 21.4047 | 36 | 7 | 9 | 3 | 52 | 32 | 10 | 12 | 15 | 21 | 177
42.913 | 5.371 | 8.0984 | 3.1107 | 42.9765 | 28.6266 | 10.1158 | 12.3822 | 14.2317 | 20.7658 | 42 | 5 | 8 | 3 | 42 | 28 | 10 | 12 | 14 | 20 | 166
52.0616 | 4.6579 | 8.1531 | 2.6443 | 55.2145 | 29.7529 | 10.5878 | 15.4753 | 16.26 | 21.0613 | 52 | 4 | 8 | 2 | 55 | 29 | 10 | 15 | 16 | 21 | 196
51.161 | 6.2993 | 10.2153 | 3.4088 | 74.1446 | 21.8646 | 9.5207 | 14.8748 | 16.0396 | 6.9692 | 51 | 6 | 10 | 3 | 74 | 21 | 9 | 14 | 16 | 6 | 192
46.9012 | 5.3138 | 9.345 | 2.7886 | 49.8426 | 29.7217 | 9.9142 | 15.9087 | 13.8178 | 16.1447 | 46 | 5 | 9 | 2 | 49 | 29 | 9 | 15 | 13 | 16 | 177
35.8222 | 5.4108 | 9.7674 | 2.7111 | 48.4345 | 30.9541 | 10.8406 | 13.7786 | 12.269 | 13.7719 | 35 | 5 | 9 | 2 | 48 | 30 | 10 | 13 | 12 | 13 | 160
41.0076 | 4.5335 | 8.9685 | 3.0565 | 56.8466 | 28.08 | 10.1988 | 14.4244 | 15.3091 | 16.7897 | 41 | 4 | 8 | 3 | 56 | 28 | 10 | 14 | 15 | 16 | 178
43.7983 | 7.025 | 8.8934 | 3.2221 | 45.7177 | 33.7717 | 9.8886 | 11.0062 | 15.9666 | 11.2904 | 43 | 7 | 8 | 3 | 45 | 33 | 9 | 11 | 15 | 11 | 166
52.0661 | 5.6831 | 12.1479 | 3.0255 | 54.9614 | 36.2579 | 9.9347 | 15.9335 | 16.5 | 9.1283 | 52 | 5 | 12 | 3 | 54 | 36 | 9 | 15 | 16 | 9 | 194
53.7198 | 6.6227 | 9.3632 | 2.8065 | 59.157 | 30.4289 | 9.8868 | 13.2707 | 14.8019 | 18.5465 | 53 | 6 | 9 | 2 | 59 | 30 | 9 | 13 | 14 | 18 | 196
44.9674 | 7.3189 | 10.3131 | 3.5518 | 57.6167 | 35.0236 | 10.0483 | 14.419 | 14.9727 | 13.603 | 44 | 7 | 10 | 3 | 57 | 35 | 10 | 14 | 14 | 13 | 187
47.2606 | 7.5748 | 7.7912 | 2.7501 | 47.5228 | 23.55 | 10.3075 | 12.8678 | 13.6918 | 22.2786 | 47 | 7 | 7 | 2 | 47 | 23 | 10 | 12 | 13 | 22 | 171
46.0445 | 5.9233 | 9.1181 | 2.4957 | 54.6463 | 38.4165 | 11.214 | 13.438 | 17.1931 | 16.7076 | 46 | 5 | 9 | 2 | 54 | 38 | 11 | 13 | 17 | 16 | 193
36.4987 | 5.7238 | 11.0974 | 2.9672 | 49.9253 | 24.7851 | 11.608 | 14.9111 | 16.4364 | 17.0899 | 36 | 5 | 11 | 2 | 49 | 24 | 11 | 14 | 16 | 17 | 167
51.6725 | 6.2344 | 10.303 | 2.9532 | 65.1503 | 24.1576 | 10.7091 | 14.6154 | 15.0103 | 19.7499 | 51 | 6 | 10 | 2 | 65 | 24 | 10 | 14 | 15 | 19 | 198
43.026 | 6.0564 | 11.9586 | 2.8633 | 52.3933 | 34.1401 | 8.2653 | 14.9787 | 15.1582 | 15.817 | 43 | 6 | 11 | 2 | 52 | 34 | 8 | 14 | 15 | 15 | 184
50.2712 | 6.464 | 8.6119 | 3.1295 | 56.8793 | 24.2175 | 10.3396 | 13.0638 | 15.607 | 13.9476 | 50 | 6 | 8 | 3 | 56 | 24 | 10 | 13 | 15 | 13 | 179
42.6088 | 6.6911 | 10.3951 | 3.0468 | 62.7348 | 30.0385 | 9.8119 | 13.1247 | 14.675 | 15.7277 | 42 | 6 | 10 | 3 | 62 | 30 | 9 | 13 | 14 | 15 | 186
41.4421 | 7.2626 | 10.8934 | 3.4223 | 68.3212 | 29.7306 | 9.9808 | 15.8159 | 13.2844 | 9.7088 | 41 | 7 | 10 | 3 | 68 | 29 | 9 | 15 | 13 | 9 | 185
41.6377 | 6.0247 | 10.174 | 2.8867 | 64.0796 | 33.203 | 10.0862 | 16.244 | 16.201 | 14.1282 | 41 | 6 | 10 | 2 | 64 | 33 | 10 | 16 | 16 | 14 | 194
45.9302 | 5.1675 | 7.8945 | 2.8003 | 60.5768 | 38.904 | 10.1627 | 14.0642 | 12.9641 | 21.7021 | 45 | 5 | 7 | 2 | 60 | 38 | 10 | 14 | 12 | 21 | 197
43.8426 | 5.7548 | 11.9187 | 2.1993 | 62.2523 | 32.1992 | 11.4955 | 13.3912 | 17.0811 | 9.9012 | 43 | 5 | 11 | 2 | 62 | 32 | 11 | 13 | 17 | 9 | 187
45.4851 | 6.7276 | 9.0728 | 2.9429 | 55.2097 | 20.9949 | 9.7286 | 14.3373 | 15.4003 | 14.3916 | 45 | 6 | 9 | 2 | 55 | 20 | 9 | 14 | 15 | 14 | 172
49.0054 | 4.8927 | 6.9522 | 2.64 | 56.4834 | 27.1088 | 10.4437 | 17.406 | 13.3921 | 17.1944 | 49 | 4 | 6 | 2 | 56 | 27 | 10 | 17 | 13 | 17 | 185
37.3575 | 6.9615 | 10.4431 | 2.8395 | 64.3841 | 31.3974 | 9.7069 | 15.381 | 14.555 | 10.0957 | 37 | 6 | 10 | 2 | 64 | 31 | 9 | 15 | 14 | 10 | 181
36.5844 | 6.4037 | 9.9295 | 3.3114 | 71.5757 | 31.1529 | 9.2613 | 13.3131 | 15.4941 | 21.574 | 36 | 6 | 9 | 3 | 71 | 31 | 9 | 13 | 15 | 21 | 196
41.099 | 6.2752 | 8.541 | 2.7594 | 70.3694 | 31.6637 | 10.539 | 15.1457 | 15.4834 | 14.36 | 41 | 6 | 8 | 2 | 70 | 31 | 10 | 15 | 15 | 14 | 194
41.7931 | 6.8568 | 11.1048 | 3.1009 | 71.1667 | 36.4677 | 8.9162 | 13.5278 | 14.0114 | 10.4997 | 41 | 6 | 11 | 3 | 71 | 36 | 8 | 13 | 14 | 10 | 196
35.6697 | 6.489 | 9.9528 | 3.1992 | 47.5952 | 35.875 | 8.6283 | 15.4816 | 14.2411 | 6.7359 | 35 | 6 | 9 | 3 | 47 | 35 | 8 | 15 | 14 | 6 | 161
52.8257 | 5.6838 | 9.1337 | 3.5381 | 52.8189 | 26.9303 | 9.9895 | 12.6362 | 15.805 | 14.4833 | 52 | 5 | 9 | 3 | 52 | 26 | 9 | 12 | 15 | 14 | 180
49.0653 | 5.8536 | 7.3077 | 3.1382 | 63.2474 | 25.7188 | 9.7801 | 15.601 | 14.533 | 12.9739 | 49 | 5 | 7 | 3 | 63 | 25 | 9 | 15 | 14 | 12 | 185
54.331 | 6.2171 | 9.1602 | 2.9363 | 64.6706 | 36.283 | 10.7433 | 14.9731 | 15.3737 | 11.4548 | 54 | 6 | 9 | 2 | 64 | 36 | 10 | 14 | 15 | 11 | 203
43.3052 | 7.34 | 9.6957 | 3.1926 | 65.9725 | 37.3012 | 10.7504 | 12.4358 | 15.2144 | 16.7528 | 43 | 7 | 9 | 3 | 65 | 37 | 10 | 12 | 15 | 16 | 197
46.3144 | 7.4749 | 10.6245 | 3.1431 | 55.4383 | 29.3257 | 9.09 | 12.5349 | 14.3409 | 16.3286 | 46 | 7 | 10 | 3 | 55 | 29 | 9 | 12 | 14 | 16 | 182
37.5597 | 6.1086 | 10.675 | 3.7159 | 61.554 | 21.5279 | 8.5329 | 17.4999 | 13.9988 | 22.2842 | 37 | 6 | 10 | 3 | 61 | 21 | 8 | 17 | 13 | 22 | 181
44.7491 | 6.017 | 9.3198 | 3.3163 | 64.9806 | 37.1521 | 10.3896 | 13.3203 | 14.3604 | 10.5417 | 44 | 6 | 9 | 3 | 64 | 37 | 10 | 13 | 14 | 10 | 191
43.051 | 7.2907 | 7.2242 | 2.9501 | 47.7375 | 35.8214 | 9.3784 | 14.263 | 16.2501 | 17.6074 | 43 | 7 | 7 | 2 | 47 | 35 | 9 | 14 | 16 | 17 | 179
36.1089 | 6.7676 | 11.4153 | 2.831 | 70.0354 | 35.0516 | 9.6489 | 13.0821 | 13.194 | 8.1291 | 36 | 6 | 11 | 2 | 70 | 35 | 9 | 13 | 13 | 8 | 186
38.8434 | 4.7348 | 12.9849 | 2.8721 | 65.5037 | 24.1374 | 8.9101 | 15.8081 | 15.708 | 12.9933 | 38 | 4 | 12 | 2 | 65 | 24 | 8 | 15 | 15 | 12 | 181
33.4249 | 5.2496 | 10.0927 | 2.7804 | 66.2266 | 21.2553 | 10.018 | 18.5786 | 15.1847 | 18.3963 | 33 | 5 | 10 | 2 | 66 | 21 | 10 | 18 | 15 | 18 | 181
37.1596 | 6.8152 | 10.1632 | 2.7183 | 43.4775 | 35.0092 | 11.4585 | 18.1489 | 14.6646 | 11.375 | 37 | 6 | 10 | 2 | 43 | 35 | 11 | 18 | 14 | 11 | 168
48.1211 | 4.7176 | 11.0702 | 2.3681 | 68.6341 | 29.4111 | 8.6902 | 16.6751 | 13.2954 | 20.9151 | 48 | 4 | 11 | 2 | 68 | 29 | 8 | 16 | 13 | 20 | 205
32.534 | 5.7132 | 9.2892 | 3.307 | 49.0404 | 35.9692 | 9.9225 | 14.2616 | 15.8466 | 15.5475 | 32 | 5 | 9 | 3 | 49 | 35 | 9 | 14 | 15 | 15 | 169
52.0102 | 6.5781 | 10.4324 | 3.2331 | 65.1469 | 37.3187 | 10.9781 | 15.1095 | 14.1762 | 16.9689 | 52 | 6 | 10 | 3 | 65 | 37 | 10 | 15 | 14 | 16 | 209
50.2181 | 6.4858 | 9.8778 | 3.2377 | 60.1565 | 31.2211 | 10.4158 | 16.8056 | 16.5813 | 16.6423 | 50 | 6 | 9 | 3 | 60 | 31 | 10 | 16 | 16 | 16 | 198
49.4174 | 4.789 | 10.3771 | 3.1324 | 63.7341 | 22.3944 | 9.9911 | 12.6948 | 15.3421 | 17.4818 | 49 | 4 | 10 | 3 | 63 | 22 | 9 | 12 | 15 | 17 | 188
46.1728 | 6.4038 | 10.2015 | 2.6119 | 58.9613 | 31.544 | 10.7167 | 14.9434 | 14.3393 | 17.846 | 46 | 6 | 10 | 2 | 58 | 31 | 10 | 14 | 14 | 17 | 190
50.2711 | 6.7968 | 11.5442 | 2.9816 | 73.1319 | 29.9096 | 10.2577 | 13.8593 | 15.6322 | 6.1898 | 50 | 6 | 11 | 2 | 73 | 29 | 10 | 13 | 15 | 6 | 197
42.9642 | 6.3294 | 12.3916 | 2.7392 | 60.4015 | 29.4499 | 10.356 | 12.8025 | 13.6051 | 18.5391 | 42 | 6 | 12 | 2 | 60 | 29 | 10 | 12 | 13 | 18 | 186
46.6721 | 6.3672 | 10.3232 | 2.7702 | 73.7757 | 27.3605 | 8.9611 | 13.3578 | 16.4584 | 10.6939 | 46 | 6 | 10 | 2 | 73 | 27 | 8 | 13 | 16 | 10 | 195
56.4858 | 6.8317 | 10.7254 | 3.0796 | 67.2407 | 30.869 | 10.039 | 15.3842 | 14.8594 | 15.0744 | 56 | 6 | 10 | 3 | 67 | 30 | 10 | 15 | 14 | 15 | 207
53.0788 | 4.8572 | 9.7192 | 3.1793 | 70.0241 | 30.5485 | 11.016 | 11.8344 | 15.8323 | 20.3076 | 53 | 4 | 9 | 3 | 70 | 30 | 11 | 11 | 15 | 20 | 208
47.8161 | 5.9186 | 8.8388 | 3.1423 | 52.6284 | 32.0188 | 10.309 | 13.1498 | 17.043 | 10.6842 | 47 | 5 | 8 | 3 | 52 | 32 | 10 | 13 | 17 | 10 | 179
43.9017 | 5.7691 | 10.268 | 2.9933 | 56.7194 | 26.444 | 10.4927 | 17.1146 | 12.4734 | 9.7477 | 43 | 5 | 10 | 2 | 56 | 26 | 10 | 17 | 12 | 9 | 173
37.0047 | 6.8054 | 10.6151 | 3.3225 | 52.1496 | 38.9785 | 11.4638 | 13.2996 | 15.7984 | 16.734 | 37 | 6 | 10 | 3 | 52 | 38 | 11 | 13 | 15 | 16 | 181
52.6213 | 6.306 | 8.7546 | 2.7868 | 58.5783 | 33.2058 | 11.6924 | 18.8284 | 15.9763 | 13.3378 | 52 | 6 | 8 | 2 | 58 | 33 | 11 | 18 | 15 | 13 | 197
36.6312 | 6.7292 | 7.9558 | 2.8697 | 69.4748 | 36.2067 | 9.4384 | 11.1042 | 16.6636 | 7.9654 | 36 | 6 | 7 | 2 | 69 | 36 | 9 | 11 | 16 | 7 | 182
47.8001 | 5.2054 | 7.1723 | 2.8545 | 57.236 | 33.7514 | 8.7705 | 15.187 | 14.4038 | 10.9455 | 47 | 5 | 7 | 2 | 57 | 33 | 8 | 15 | 14 | 10 | 183
38.6805 | 7.0901 | 7.6011 | 2.9552 | 62.2534 | 37.5412 | 10.7299 | 11.4209 | 14.3614 | 10.2288 | 38 | 7 | 7 | 2 | 62 | 37 | 10 | 11 | 14 | 10 | 179
45.0585 | 6.3281 | 9.4016 | 3.4545 | 60.9838 | 31.5358 | 9.8906 | 13.3189 | 14.6544 | 10.6827 | 45 | 6 | 9 | 3 | 60 | 31 | 9 | 13 | 14 | 10 | 182
50.846 | 6.0625 | 10.7257 | 2.8271 | 56.7068 | 22.6165 | 9.0018 | 15.6659 | 14.364 | 15.0107 | 50 | 6 | 10 | 2 | 56 | 22 | 9 | 15 | 14 | 15 | 182
44.9203 | 7.2283 | 11.7804 | 3.0796 | 58.4146 | 35.8043 | 9.3699 | 14.8717 | 15.4975 | 22.5704 | 44 | 7 | 11 | 3 | 58 | 35 | 9 | 14 | 15 | 22 | 199
47.4246 | 5.8954 | 10.583 | 2.8509 | 70.3409 | 36.9162 | 9.0294 | 17.5473 | 15.2267 | 10.7689 | 47 | 5 | 10 | 2 | 70 | 36 | 9 | 17 | 15 | 10 | 205
42.5092 | 5.6362 | 10.2816 | 3.086 | 47.5093 | 36.8983 | 10.1458 | 14.1791 | 15.6019 | 14.3412 | 42 | 5 | 10 | 3 | 47 | 36 | 10 | 14 | 15 | 14 | 178
43.4252 | 6.7845 | 11.5505 | 3.3072 | 71.2918 | 28.5821 | 10.9274 | 11.1104 | 14.5209 | 14.8403 | 43 | 6 | 11 | 3 | 71 | 28 | 10 | 11 | 14 | 14 | 192
57.5284 | 5.2799 | 8.152 | 3.2239 | 60.3887 | 33.3529 | 10.5954 | 13.7212 | 16.4 | 16.8382 | 57 | 5 | 8 | 3 | 60 | 33 | 10 | 13 | 16 | 16 | 203
47.8211 | 4.6551 | 8.3176 | 2.658 | 49.2649 | 27.2461 | 8.7951 | 17.7365 | 13.7564 | 14.8582 | 47 | 4 | 8 | 2 | 49 | 27 | 8 | 17 | 13 | 14 | 175
42.6278 | 6.3637 | 11.0291 | 2.7407 | 65.8275 | 28.8484 | 9.6273 | 17.3722 | 12.5398 | 9.9237 | 42 | 6 | 11 | 2 | 65 | 28 | 9 | 17 | 12 | 9 | 184
33.133 | 4.6372 | 9.8603 | 3.4217 | 75.0166 | 35.6692 | 9.7219 | 13.2136 | 14.874 | 18.4518 | 33 | 4 | 9 | 3 | 75 | 35 | 9 | 13 | 14 | 18 | 197
49.0327 | 5.8311 | 11.0709 | 2.5713 | 59.0753 | 30.8554 | 10.8406 | 14.3941 | 16.1641 | 11.1059 | 49 | 5 | 11 | 2 | 59 | 30 | 10 | 14 | 16 | 11 | 190
34.2907 | 4.7097 | 8.6915 | 2.1946 | 57.5582 | 30.276 | 10.783 | 15.3784 | 14.5253 | 12.5964 | 34 | 4 | 8 | 2 | 57 | 30 | 10 | 15 | 14 | 12 | 170
53.0551 | 4.9041 | 10.2388 | 3.1105 | 63.418 | 37.8683 | 10.1892 | 14.4544 | 14.8387 | 14.502 | 53 | 4 | 10 | 3 | 63 | 37 | 10 | 14 | 14 | 14 | 205
48.0775 | 5.6796 | 9.5582 | 2.9359 | 74.5944 | 34.0308 | 9.4338 | 13.018 | 17.6902 | 16.5227 | 48 | 5 | 9 | 2 | 74 | 34 | 9 | 13 | 17 | 16 | 211
47.6317 | 6.6714 | 10.0746 | 2.48 | 75.1784 | 30.3992 | 9.8642 | 15.5664 | 14.4153 | 13.4822 | 47 | 6 | 10 | 2 | 75 | 30 | 9 | 15 | 14 | 13 | 204
55.4618 | 5.6131 | 10.6972 | 2.4859 | 54.4878 | 26.7093 | 10.3527 | 16.0089 | 15.0842 | 6.7644 | 55 | 5 | 10 | 2 | 54 | 26 | 10 | 16 | 15 | 6 | 182
40.3939 | 6.2704 | 9.4111 | 2.8491 | 50.7628 | 23.2019 | 9.7732 | 15.5031 | 15.4249 | 15.6724 | 40 | 6 | 9 | 2 | 50 | 23 | 9 | 15 | 15 | 15 | 167
53.247 | 6.6471 | 7.925 | 3.3652 | 67.9397 | 31.9541 | 9.8495 | 15.6888 | 14.1443 | 13.0008 | 53 | 6 | 7 | 3 | 67 | 31 | 9 | 15 | 14 | 13 | 200
40.8158 | 5.7773 | 10.7985 | 3.488 | 72.8436 | 37.7834 | 9.4668 | 16.2001 | 16.1681 | 16.0005 | 40 | 5 | 10 | 3 | 72 | 37 | 9 | 16 | 16 | 16 | 207
43.387 | 5.8636 | 8.3544 | 3.0818 | 66.6446 | 26.9451 | 9.9886 | 13.8816 | 16.5123 | 19.8624 | 43 | 5 | 8 | 3 | 66 | 26 | 9 | 13 | 16 | 19 | 191
38.7293 | 6.8377 | 11.9347 | 3.6929 | 65.896 | 36.8444 | 10.9671 | 17.7728 | 15.5023 | 13.6138 | 38 | 6 | 11 | 3 | 65 | 36 | 10 | 17 | 15 | 13 | 195
50.7425 | 6.6982 | 7.2485 | 3.5727 | 41.7136 | 27.0196 | 10.6606 | 13.8096 | 15.9997 | 17.1203 | 50 | 6 | 7 | 3 | 41 | 27 | 10 | 13 | 15 | 17 | 170
40.434 | 7.3856 | 11.2281 | 2.9582 | 44.4297 | 36.0902 | 11.3905 | 13.6675 | 14.0513 | 19.3774 | 40 | 7 | 11 | 2 | 44 | 36 | 11 | 13 | 14 | 19 | 177
45.9165 | 5.1601 | 8.4564 | 2.7323 | 44.3982 | 26.2074 | 11.0183 | 17.7251 | 14.5613 | 14.7241 | 45 | 5 | 8 | 2 | 44 | 26 | 11 | 17 | 14 | 14 | 168
54.2772 | 6.6514 | 11.1494 | 2.3049 | 66.7411 | 33.2733 | 10.1468 | 14.0829 | 14.54 | 23.2478 | 54 | 6 | 11 | 2 | 66 | 33 | 10 | 14 | 14 | 23 | 215
40.8619 | 5.2432 | 11.7385 | 2.6883 | 71.9026 | 29.689 | 9.6173 | 15.0313 | 12.8466 | 16.6866 | 40 | 5 | 11 | 2 | 71 | 29 | 9 | 15 | 12 | 16 | 194
43.039 | 4.7734 | 11.1129 | 2.8721 | 64.132 | 28.0064 | 11.1689 | 16.8981 | 14.5487 | 21.0186 | 43 | 4 | 11 | 2 | 64 | 28 | 11 | 16 | 14 | 21 | 197
49.9019 | 6.5639 | 7.5656 | 2.9693 | 57.3782 | 38.076 | 10.4483 | 13.8297 | 15.7055 | 18.0561 | 49 | 6 | 7 | 2 | 57 | 38 | 10 | 13 | 15 | 18 | 197
49.7583 | 6.3929 | 7.2099 | 3.1452 | 70.9558 | 23.2433 | 9.9586 | 15.7856 | 14.6108 | 13.8608 | 49 | 6 | 7 | 3 | 70 | 23 | 9 | 15 | 14 | 13 | 191
44.7796 | 4.9177 | 8.5469 | 2.7141 | 64.667 | 29.5073 | 8.9 | 13.2943 | 13.9337 | 10.3608 | 44 | 4 | 8 | 2 | 64 | 29 | 8 | 13 | 13 | 10 | 181
44.7601 | 6.0148 | 6.9351 | 3.0156 | 57.0796 | 35.5073 | 10.7485 | 13.5887 | 16.2643 | 19.2128 | 44 | 6 | 6 | 3 | 57 | 35 | 10 | 13 | 16 | 19 | 190
37.4849 | 6.864 | 9.0752 | 3.2173 | 60.4803 | 33.6448 | 10.3505 | 11.8008 | 16.7409 | 17.7575 | 37 | 6 | 9 | 3 | 60 | 33 | 10 | 11 | 16 | 17 | 183
37.8661 | 5.2283 | 9.518 | 2.7612 | 53.5673 | 34.4558 | 9.4095 | 17.5189 | 16.0432 | 14.3598 | 37 | 5 | 9 | 2 | 53 | 34 | 9 | 17 | 16 | 14 | 180
40.6085 | 5.387 | 8.5828 | 3.3148 | 67.5118 | 23.0378 | 8.8899 | 14.9146 | 13.3625 | 12.713 | 40 | 5 | 8 | 3 | 67 | 23 | 8 | 14 | 13 | 12 | 177
48.0042 | 6.5873 | 12.8804 | 3.0889 | 60.9084 | 27.8887 | 8.4998 | 13.1117 | 16.6547 | 21.6708 | 48 | 6 | 12 | 3 | 60 | 27 | 8 | 13 | 16 | 21 | 197
43.9574 | 6.362 | 9.9415 | 3.1721 | 74.5179 | 28.2048 | 8.9911 | 15.2768 | 15.0583 | 8.7468 | 43 | 6 | 9 | 3 | 74 | 28 | 8 | 15 | 15 | 8 | 192
38.5767 | 5.1103 | 12.0913 | 2.8013 | 46.5343 | 31.7984 | 10.7939 | 12.6895 | 12.3265 | 14.4329 | 38 | 5 | 12 | 2 | 46 | 31 | 10 | 12 | 12 | 14 | 165
34.5886 | 4.785 | 11.117 | 3.7973 | 63.7904 | 31.7384 | 9.7317 | 14.6834 | 14.172 | 16.525 | 34 | 4 | 11 | 3 | 63 | 31 | 9 | 14 | 14 | 16 | 183
32.8177 | 5.6179 | 9.6435 | 3.0496 | 54.0136 | 31.4005 | 8.6484 | 16.3389 | 13.9308 | 13.9959 | 32 | 5 | 9 | 3 | 54 | 31 | 8 | 16 | 13 | 13 | 168
46.7019 | 7.4987 | 6.8477 | 2.9693 | 74.581 | 24.2508 | 8.1025 | 17.3841 | 15.5467 | 15.3917 | 46 | 7 | 6 | 2 | 74 | 24 | 8 | 17 | 15 | 15 | 197
45.6366 | 5.3755 | 10.2342 | 2.8456 | 58.0999 | 33.0562 | 8.8282 | 15.6095 | 15.0258 | 17.0628 | 45 | 5 | 10 | 2 | 58 | 33 | 8 | 15 | 15 | 17 | 193
40.8349 | 5.8977 | 13.2778 | 2.8438 | 63.052 | 29.6071 | 9.6478 | 12.2762 | 15.0735 | 12.7932 | 40 | 5 | 13 | 2 | 63 | 29 | 9 | 12 | 15 | 12 | 184
42.1688 | 6.6988 | 10.249 | 3.9763 | 49.042 | 32.0007 | 10.4173 | 17.8567 | 13.7577 | 11.9558 | 42 | 6 | 10 | 3 | 49 | 32 | 10 | 17 | 13 | 11 | 174
45.569 | 7.134 | 13.4034 | 2.986 | 68.3938 | 32.8598 | 10.5469 | 15.8021 | 16.6538 | 13.6856 | 45 | 7 | 13 | 2 | 68 | 32 | 10 | 15 | 16 | 13 | 202
35.1021 | 5.6276 | 8.8698 | 2.7659 | 71.4473 | 34.2106 | 8.8681 | 11.3921 | 13.9888 | 10.3065 | 35 | 5 | 8 | 2 | 71 | 34 | 8 | 11 | 13 | 10 | 182
49.694 | 6.1696 | 13.3499 | 3.1311 | 76.165 | 23.1384 | 9.852 | 16.8306 | 14.8313 | 18.3536 | 49 | 6 | 13 | 3 | 76 | 23 | 9 | 16 | 14 | 18 | 209
42.7756 | 6.1532 | 10.7172 | 2.7335 | 72.9351 | 29.4348 | 11.5789 | 17.3305 | 13.0804 | 5.4759 | 42 | 6 | 10 | 2 | 72 | 29 | 11 | 17 | 13 | 5 | 188
40.2099 | 7.0551 | 9.4839 | 3.1519 | 62.9154 | 29.0799 | 8.985 | 15.1448 | 16.091 | 12.2316 | 40 | 7 | 9 | 3 | 62 | 29 | 8 | 15 | 16 | 12 | 183
44.8613 | 7.5245 | 9.9951 | 2.54 | 71.8634 | 35.4908 | 9.2358 | 16.5188 | 14.2106 | 17.608 | 44 | 7 | 9 | 2 | 71 | 35 | 9 | 16 | 14 | 17 | 206
43.2107 | 6.9596 | 11.3227 | 3.1573 | 58.2357 | 29.7186 | 9.9556 | 14.4056 | 15.868 | 16.3863 | 43 | 6 | 11 | 3 | 58 | 29 | 9 | 14 | 15 | 16 | 186
34.1959 | 6.922 | 12.0936 | 2.9144 | 54.3415 | 28.6045 | 10.4631 | 14.1074 | 17.1133 | 9.5231 | 34 | 6 | 12 | 2 | 54 | 28 | 10 | 14 | 17 | 9 | 168
51.2477 | 5.8279 | 8.4109 | 3.0042 | 68.6463 | 33.1059 | 9.0018 | 13.0612 | 16.1277 | 16.1401 | 51 | 5 | 8 | 3 | 68 | 33 | 9 | 13 | 16 | 16 | 205
48.316 | 6.1039 | 11.6333 | 2.5538 | 61.321 | 37.2083 | 9.4452 | 13.3838 | 16.3811 | 9.1917 | 48 | 6 | 11 | 2 | 61 | 37 | 9 | 13 | 16 | 9 | 195
39.3023 | 7.6007 | 10.0032 | 3.185 | 55.6653 | 29.621 | 8.5124 | 12.1364 | 15.9063 | 15.9119 | 39 | 7 | 10 | 3 | 55 | 29 | 8 | 12 | 15 | 15 | 175
49.9091 | 5.4285 | 9.9873 | 3.4608 | 68.0416 | 32.4116 | 9.0977 | 15.3056 | 15.4952 | 17.0691 | 49 | 5 | 9 | 3 | 68 | 32 | 9 | 15 | 15 | 17 | 205
49.6914 | 5.9941 | 10.5077 | 2.3202 | 78.0701 | 24.5546 | 9.2026 | 16.4971 | 15.5855 | 8.6054 | 49 | 5 | 10 | 2 | 78 | 24 | 9 | 16 | 15 | 8 | 200
39.4587 | 7.2674 | 8.1009 | 2.8088 | 60.7792 | 32.3786 | 10.7123 | 15.1657 | 17.3559 | 11.946 | 39 | 7 | 8 | 2 | 60 | 32 | 10 | 15 | 17 | 11 | 182
48.4298 | 6.7631 | 10.3914 | 3.3301 | 74.3221 | 27.3934 | 9.9677 | 17.6369 | 15.1236 | 15.8558 | 48 | 6 | 10 | 3 | 74 | 27 | 9 | 17 | 15 | 15 | 206
33.2143 | 5.4917 | 11.0753 | 3.0595 | 61.0518 | 24.2754 | 11.0177 | 17.7379 | 14.9385 | 13.3881 | 33 | 5 | 11 | 3 | 61 | 24 | 11 | 17 | 14 | 13 | 173
43.3018 | 4.5536 | 11.0456 | 2.2738 | 78.3212 | 26.4311 | 10.0329 | 14.9981 | 16.7227 | 12.1198 | 43 | 4 | 11 | 2 | 78 | 26 | 10 | 14 | 16 | 12 | 200
51.3474 | 6.0244 | 7.8042 | 2.7947 | 55.2819 | 27.9774 | 10.4079 | 14.013 | 13.3347 | 11.2005 | 51 | 6 | 7 | 2 | 55 | 27 | 10 | 14 | 13 | 11 | 178
51.9199 | 5.7512 | 12.0074 | 3.2575 | 57.7851 | 32.1497 | 10.5722 | 14.5457 | 15.2723 | 14.0607 | 51 | 5 | 12 | 3 | 57 | 32 | 10 | 14 | 15 | 14 | 195
40.774 | 7.2213 | 10.1631 | 2.7292 | 64.8633 | 28.6055 | 9.3015 | 16.727 | 14.8268 | 14.0767 | 40 | 7 | 10 | 2 | 64 | 28 | 9 | 16 | 14 | 14 | 186
46.8631 | 5.1098 | 11.3763 | 2.7066 | 52.5067 | 30.1439 | 10.6719 | 16.7159 | 15.5772 | 20.4312 | 46 | 5 | 11 | 2 | 52 | 30 | 10 | 16 | 15 | 20 | 190
56.0729 | 5.2575 | 10.4179 | 2.7235 | 64.3846 | 34.4816 | 10.1221 | 13.3082 | 13.8329 | 18.2766 | 56 | 5 | 10 | 2 | 64 | 34 | 10 | 13 | 13 | 18 | 208
46.4672 | 5.7466 | 6.091 | 2.719 | 61.3179 | 30.6878 | 10.4897 | 15.8317 | 12.9055 | 12.7955 | 46 | 5 | 6 | 2 | 61 | 30 | 10 | 15 | 12 | 12 | 182
43.3842 | 4.9546 | 13.0853 | 2.822 | 62.2468 | 37.9549 | 11.1108 | 18.0116 | 14.8599 | 12.1802 | 43 | 4 | 13 | 2 | 62 | 37 | 11 | 18 | 14 | 12 | 199
37.521 | 5.2676 | 10.0501 | 3.7466 | 48.7006 | 23.6214 | 10.0591 | 16.5055 | 13.6245 | 9.6819 | 37 | 5 | 10 | 3 | 48 | 23 | 10 | 16 | 13 | 9 | 156
53.1873 | 6.3531 | 8.9043 | 2.9939 | 73.5952 | 27.975 | 10.2278 | 10.7012 | 14.6561 | 17.0647 | 53 | 6 | 8 | 2 | 73 | 27 | 10 | 10 | 14 | 17 | 202
44.3198 | 5.7107 | 10.5821 | 2.4845 | 76.6257 | 35.7352 | 11.4124 | 12.5133 | 15.2181 | 14.9581 | 44 | 5 | 10 | 2 | 76 | 35 | 11 | 12 | 15 | 14 | 206
39.8233 | 5.9968 | 12.8422 | 3.3174 | 66.6804 | 26.1696 | 8.955 | 17.4631 | 13.4799 | 12.7024 | 39 | 5 | 12 | 3 | 66 | 26 | 8 | 17 | 13 | 12 | 185
37.6797 | 6.7556 | 10.84 | 3.3861 | 72.7323 | 28.1393 | 9.4228 | 13.5409 | 16.8905 | 17.0899 | 37 | 6 | 10 | 3 | 72 | 28 | 9 | 13 | 16 | 17 | 193
48.6473 | 5.0905 | 10.5635 | 2.2176 | 44.4482 | 26.3703 | 11.6322 | 16.6422 | 16.1879 | 8.2039 | 48 | 5 | 10 | 2 | 44 | 26 | 11 | 16 | 16 | 8 | 168
46.6031 | 7.5476 | 8.0849 | 2.5816 | 69.9533 | 37.6053 | 11.8543 | 15.8482 | 14.4899 | 15.0394 | 46 | 7 | 8 | 2 | 69 | 37 | 11 | 15 | 14 | 15 | 204
34.6625 | 7.0056 | 10.9619 | 3.2782 | 66.6253 | 33.7229 | 11.3759 | 15.4397 | 14.6301 | 15.5087 | 34 | 7 | 10 | 3 | 66 | 33 | 11 | 15 | 14 | 15 | 187
49.3585 | 7.7851 | 10.3439 | 3.664 | 50.4074 | 24.1862 | 9.714 | 19.1515 | 15.9741 | 17.0643 | 49 | 7 | 10 | 3 | 50 | 24 | 9 | 19 | 15 | 17 | 184
44.5746 | 5.4439 | 11.4569 | 2.8508 | 45.828 | 32.1596 | 10.5164 | 12.9747 | 15.6947 | 10.0788 | 44 | 5 | 11 | 2 | 45 | 32 | 10 | 12 | 15 | 10 | 169
50.4752 | 4.3458 | 9.2956 | 3.877 | 49.4961 | 33.7559 | 9.5948 | 13.3269 | 14.4091 | 16.941 | 50 | 4 | 9 | 3 | 49 | 33 | 9 | 13 | 14 | 16 | 184
56.2393 | 6.1628 | 9.5206 | 2.2901 | 58.8184 | 25.601 | 11.4569 | 12.6868 | 16.4478 | 13.9719 | 56 | 6 | 9 | 2 | 58 | 25 | 11 | 12 | 16 | 13 | 189
38.5948 | 5.1273 | 11.7884 | 2.0406 | 61.8167 | 38.8392 | 11.4468 | 15.5234 | 15.0811 | 16.1195 | 38 | 5 | 11 | 2 | 61 | 38 | 11 | 15 | 15 | 16 | 194
55.9128 | 6.9 | 11.4651 | 2.9331 | 64.6814 | 26.741 | 9.9999 | 13.3091 | 12.5143 | 7.9967 | 55 | 6 | 11 | 2 | 64 | 26 | 9 | 13 | 12 | 7 | 188
40.0097 | 5.4024 | 6.2347 | 2.8811 | 57.3001 | 35.8726 | 8.5336 | 15.9003 | 15.5428 | 13.2807 | 40 | 5 | 6 | 2 | 57 | 35 | 8 | 15 | 15 | 13 | 181
38.7264 | 4.9458 | 9.7488 | 3.1625 | 73.5945 | 32.0639 | 10.1909 | 11.9742 | 12.2238 | 10.4859 | 38 | 4 | 9 | 3 | 73 | 32 | 10 | 11 | 12 | 10 | 185
39.6839 | 6.117 | 9.9868 | 2.6798 | 55.967 | 37.8238 | 8.4106 | 14.1883 | 15.639 | 18.0806 | 39 | 6 | 9 | 2 | 55 | 37 | 8 | 14 | 15 | 18 | 187
44.8412 | 4.5569 | 8.9643 | 2.5034 | 57.1781 | 27.8624 | 11.1438 | 13.3483 | 14.1064 | 15.2905 | 44 | 4 | 8 | 2 | 57 | 27 | 11 | 13 | 14 | 15 | 178
40.3094 | 4.8365 | 11.9711 | 3.0187 | 46.4359 | 38.3558 | 9.0535 | 17.3838 | 14.1882 | 16.7293 | 40 | 4 | 11 | 3 | 46 | 38 | 9 | 17 | 14 | 16 | 182
46.1446 | 7.7451 | 9.0769 | 3.2456 | 63.0609 | 33.6746 | 10.1324 | 14.1654 | 13.6576 | 22.5422 | 46 | 7 | 9 | 3 | 63 | 33 | 10 | 14 | 13 | 22 | 200
52.2744 | 5.0752 | 11.0414 | 2.9765 | 60.6997 | 23.9995 | 11.1215 | 16.1741 | 12.1703 | 18.0492 | 52 | 5 | 11 | 2 | 60 | 23 | 11 | 16 | 12 | 18 | 192
54.6247 | 6.7505 | 9.9895 | 2.2989 | 50.1209 | 23.2247 | 9.8243 | 13.2833 | 14.2613 | 8.6503 | 54 | 6 | 9 | 2 | 50 | 23 | 9 | 13 | 14 | 8 | 171
41.6537 | 6.0729 | 8.0976 | 3.0608 | 69.1921 | 25.2758 | 10.1216 | 14.3201 | 16.4049 | 13.7581 | 41 | 6 | 8 | 3 | 69 | 25 | 10 | 14 | 16 | 13 | 186
45.1626 | 6.1065 | 7.7903 | 3.231 | 65.8336 | 29.1755 | 10.1037 | 15.3953 | 16.2051 | 16.7963 | 45 | 6 | 7 | 3 | 65 | 29 | 10 | 15 | 16 | 16 | 193
48.1409 | 6.3077 | 8.5288 | 3.6352 | 69.2272 | 34.4906 | 9.745 | 13.9326 | 14.4099 | 12.4101 | 48 | 6 | 8 | 3 | 69 | 34 | 9 | 13 | 14 | 12 | 198
45.0915 | 5.908 | 12.7721 | 2.2621 | 64.5009 | 30.9941 | 10.1266 | 16.4602 | 14.028 | 18.0177 | 45 | 5 | 12 | 2 | 64 | 30 | 10 | 16 | 14 | 18 | 199
50.1893 | 5.801 | 7.6875 | 2.6985 | 56.0906 | 28.7272 | 11.2681 | 12.2928 | 17.0237 | 15.7759 | 50 | 5 | 7 | 2 | 56 | 28 | 11 | 12 | 17 | 15 | 185
55.0903 | 6.3048 | 12.2244 | 3.3664 | 64.5071 | 32.5964 | 11.1477 | 15.4939 | 14.2533 | 12.8413 | 55 | 6 | 12 | 3 | 64 | 32 | 11 | 15 | 14 | 12 | 204
55.4336 | 7.3248 | 12.284 | 2.6559 | 57.4712 | 23.0255 | 10.0226 | 17.7864 | 16.2914 | 10.3738 | 55 | 7 | 12 | 2 | 57 | 23 | 10 | 17 | 16 | 10 | 190
43.438 | 5.2765 | 13.7268 | 3.2559 | 59.1022 | 37.0204 | 10.6495 | 14.1553 | 16.2505 | 13.4952 | 43 | 5 | 13 | 3 | 59 | 37 | 10 | 14 | 16 | 13 | 195
42.8384 | 4.5502 | 10.0111 | 3.8007 | 61.6078 | 34.1537 | 9.2745 | 17.0012 | 16.5941 | 21.2133 | 42 | 4 | 10 | 3 | 61 | 34 | 9 | 17 | 16 | 21 | 201
48.8407 | 7.2474 | 10.8001 | 2.3566 | 62.9945 | 34.2781 | 10.1729 | 16.0545 | 14.7397 | 13.7509 | 48 | 7 | 10 | 2 | 62 | 34 | 10 | 16 | 14 | 13 | 197
52.733 | 4.5816 | 10.1802 | 2.4078 | 48.314 | 23.1851 | 10.6035 | 11.1791 | 13.749 | 13.904 | 52 | 4 | 10 | 2 | 48 | 23 | 10 | 11 | 13 | 13 | 170
47.8852 | 6.11 | 8.1006 | 2.9066 | 62.4915 | 33.4401 | 8.5889 | 15.4712 | 15.2185 | 15.5289 | 47 | 6 | 8 | 2 | 62 | 33 | 8 | 15 | 15 | 15 | 195
52.3796 | 5.427 | 10.2055 | 3.0581 | 59.4943 | 22.4914 | 9.0888 | 12.8239 | 16.1234 | 15.8096 | 52 | 5 | 10 | 3 | 59 | 22 | 9 | 12 | 16 | 15 | 186
54.1001 | 6.0209 | 6.7202 | 2.9433 | 62.8666 | 34.432 | 9.3822 | 17.8188 | 15.6621 | 17.5212 | 54 | 6 | 6 | 2 | 62 | 34 | 9 | 17 | 15 | 17 | 205
37.501 | 4.432 | 8.9123 | 3.1363 | 62.1841 | 30.2548 | 9.7626 | 11.0954 | 12.9799 | 8.9574 | 37 | 4 | 8 | 3 | 62 | 30 | 9 | 11 | 12 | 8 | 168
50.8129 | 5.8895 | 12.0661 | 3.6461 | 61.3687 | 32.6677 | 10.6932 | 13.5955 | 14.1834 | 7.1012 | 50 | 5 | 12 | 3 | 61 | 32 | 10 | 13 | 14 | 7 | 189
48.5529 | 5.7536 | 12.5513 | 2.9331 | 71.3737 | 27.0028 | 10.9111 | 17.8774 | 14.0028 | 15.1318 | 48 | 5 | 12 | 2 | 71 | 27 | 10 | 17 | 14 | 15 | 204
49.9853 | 4.5674 | 10.5986 | 2.9783 | 76.0453 | 30.4409 | 10.4294 | 15.9094 | 14.6759 | 16.6258 | 49 | 4 | 10 | 2 | 76 | 30 | 10 | 15 | 14 | 16 | 210
41.1828 | 5.0791 | 9.9117 | 3.5123 | 56.3999 | 30.2183 | 10.6078 | 13.4514 | 15.364 | 16.8529 | 41 | 5 | 9 | 3 | 56 | 30 | 10 | 13 | 15 | 16 | 180
46.6258 | 6.0503 | 10.7027 | 3.3554 | 61.1194 | 30.9108 | 10.8672 | 13.338 | 14.8525 | 9.9337 | 46 | 6 | 10 | 3 | 61 | 30 | 10 | 13 | 14 | 9 | 183
44.2589 | 4.4662 | 10.4472 | 3.6922 | 61.6978 | 38.3215 | 9.4918 | 12.7834 | 14.1629 | 14.5959 | 44 | 4 | 10 | 3 | 61 | 38 | 9 | 12 | 14 | 14 | 193
30.6555 | 7.2033 | 10.0103 | 2.1817 | 52.5832 | 27.1342 | 10.2231 | 13.0866 | 16.7652 | 8.2695 | 30 | 7 | 10 | 2 | 52 | 27 | 10 | 13 | 16 | 8 | 156
44.7786 | 6.0224 | 9.6803 | 3.3284 | 77.5175 | 24.5678 | 9.1663 | 17.4121 | 14.7776 | 23.4882 | 44 | 6 | 9 | 3 | 77 | 24 | 9 | 17 | 14 | 23 | 208
43.9685 | 6.4351 | 10.8513 | 2.3372 | 54.4857 | 32.1341 | 9.5638 | 14.6705 | 15.8439 | 22.9244 | 43 | 6 | 10 | 2 | 54 | 32 | 9 | 14 | 15 | 22 | 190
42.4823 | 6.6825 | 11.5918 | 3.3015 | 56.0967 | 34.4009 | 11.1537 | 13.4942 | 14.2816 | 20.2486 | 42 | 6 | 11 | 3 | 56 | 34 | 11 | 13 | 14 | 20 | 190
55.398 | 6.6264 | 9.3395 | 3.0174 | 59.2431 | 28.3 | 11.0227 | 18.0705 | 15.7367 | 6.0347 | 55 | 6 | 9 | 3 | 59 | 28 | 11 | 18 | 15 | 6 | 190
38.7325 | 4.9221 | 6.5146 | 2.2539 | 53.721 | 27.9974 | 9.5248 | 16.6017 | 14.2522 | 16.914 | 38 | 4 | 6 | 2 | 53 | 27 | 9 | 16 | 14 | 16 | 170
42.5387 | 5.2051 | 9.312 | 3.0289 | 45.6781 | 28.0257 | 9.9843 | 16.8869 | 14.7409 | 9.4772 | 42 | 5 | 9 | 3 | 45 | 28 | 9 | 16 | 14 | 9 | 163
39.1812 | 6.2877 | 6.9373 | 3.7939 | 67.1519 | 29.9996 | 11.2827 | 12.1135 | 15.045 | 13.1145 | 39 | 6 | 6 | 3 | 67 | 29 | 11 | 12 | 15 | 13 | 181
48.4047 | 5.9105 | 9.0182 | 3.7287 | 57.1541 | 27.7985 | 10.4556 | 15.5508 | 15.0017 | 19.1875 | 48 | 5 | 9 | 3 | 57 | 27 | 10 | 15 | 15 | 19 | 190
44.4236 | 5.4499 | 9.5604 | 2.792 | 58.644 | 33.6996 | 11.1624 | 17.5845 | 14.0086 | 10.9547 | 44 | 5 | 9 | 2 | 58 | 33 | 11 | 17 | 14 | 10 | 185
53.1126 | 4.989 | 9.2619 | 2.4825 | 55.6307 | 23.8945 | 10.6626 | 18.9903 | 17.0618 | 13.2151 | 53 | 4 | 9 | 2 | 55 | 23 | 10 | 18 | 17 | 13 | 188
48.0645 | 5.5012 | 11.1042 | 3.3455 | 61.5762 | 29.8203 | 9.4737 | 13.6957 | 14.5682 | 12.148 | 48 | 5 | 11 | 3 | 61 | 29 | 9 | 13 | 14 | 12 | 188
44.2913 | 6.262 | 7.5519 | 3.0247 | 55.4759 | 35.1801 | 9.2033 | 12.6212 | 14.9155 | 11.4776 | 44 | 6 | 7 | 3 | 55 | 35 | 9 | 12 | 14 | 11 | 178
53.733 | 5.2047 | 8.2573 | 3.3981 | 50.1657 | 31.6392 | 10.3802 | 15.0016 | 15.8045 | 18.3171 | 53 | 5 | 8 | 3 | 50 | 31 | 10 | 15 | 15 | 18 | 190
46.3049 | 5.4508 | 9.9648 | 2.703 | 66.4415 | 28.2945 | 9.7861 | 15.4524 | 14.8015 | 16.4064 | 46 | 5 | 9 | 2 | 66 | 28 | 9 | 15 | 14 | 16 | 194
35.2556 | 6.3727 | 9.1392 | 3.7667 | 76.4961 | 24.4746 | 10.2125 | 12.7042 | 17.8638 | 12.5947 | 35 | 6 | 9 | 3 | 76 | 24 | 10 | 12 | 17 | 12 | 185
43.3125 | 6.7892 | 9.1425 | 3.1207 | 57.4673 | 31.4925 | 8.4545 | 14.0738 | 14.9817 | 14.676 | 43 | 6 | 9 | 3 | 57 | 31 | 8 | 14 | 14 | 14 | 182
46.9633 | 6.8881 | 7.9265 | 2.8521 | 55.943 | 29.9146 | 10.8659 | 13.0298 | 14.5468 | 12.4488 | 46 | 6 | 7 | 2 | 55 | 29 | 10 | 13 | 14 | 12 | 176
47.3956 | 5.9689 | 9.9095 | 2.7846 | 59.2649 | 30.6119 | 8.8825 | 16.4071 | 15.8808 | 12.523 | 47 | 5 | 9 | 2 | 59 | 30 | 8 | 16 | 15 | 12 | 188
55.1315 | 5.6471 | 12.598 | 2.703 | 58.0458 | 32.3693 | 11.5934 | 17.2267 | 17.1425 | 15.2282 | 55 | 5 | 12 | 2 | 58 | 32 | 11 | 17 | 17 | 15 | 206
52.5389 | 6.2782 | 11.7406 | 3.2013 | 59.5 | 39.1425 | 9.4924 | 16.5099 | 12.9082 | 7.1933 | 52 | 6 | 11 | 3 | 59 | 39 | 9 | 16 | 12 | 7 | 196
43.0761 | 5.2231 | 8.5528 | 2.7777 | 51.2489 | 25.1633 | 11.2266 | 15.1328 | 17.3238 | 19.5551 | 43 | 5 | 8 | 2 | 51 | 25 | 11 | 15 | 17 | 19 | 178
40.3049 | 5.55 | 9.9851 | 3.2813 | 58.298 | 29.1028 | 10.6969 | 14.7828 | 15.2797 | 13.7316 | 40 | 5 | 9 | 3 | 58 | 29 | 10 | 14 | 15 | 13 | 178
47.8377 | 5.3698 | 8.0216 | 3.0251 | 68.9801 | 29.0088 | 9.5496 | 13.6716 | 15.4551 | 11.5993 | 47 | 5 | 8 | 3 | 68 | 29 | 9 | 13 | 15 | 11 | 191
55.8385 | 5.5316 | 10.7823 | 3.5235 | 64.2812 | 27.595 | 9.9391 | 15.165 | 15.4966 | 16.1064 | 55 | 5 | 10 | 3 | 64 | 27 | 9 | 15 | 15 | 16 | 202
50.6172 | 5.8979 | 9.6882 | 3.05 | 65.3678 | 36.8243 | 9.8612 | 17.041 | 15.4819 | 23.4365 | 50 | 5 | 9 | 3 | 65 | 36 | 9 | 17 | 15 | 23 | 215
40.8062 | 7.6907 | 8.6406 | 3.9262 | 69.1545 | 33.1835 | 9.5846 | 18.9623 | 15.3523 | 14.0218 | 40 | 7 | 8 | 3 | 69 | 33 | 9 | 18 | 15 | 14 | 197
53.7132 | 5.9741 | 10.1658 | 2.0449 | 59.4551 | 28.4857 | 9.0202 | 14.3126 | 13.6171 | 14.919 | 53 | 5 | 10 | 2 | 59 | 28 | 9 | 14 | 13 | 14 | 191
33.4235 | 6.2473 | 12.5816 | 3.6849 | 59.5089 | 34.8787 | 9.9679 | 14.9713 | 14.1568 | 7.5137 | 33 | 6 | 12 | 3 | 59 | 34 | 9 | 14 | 14 | 7 | 173
37.6402 | 6.7833 | 8.6471 | 2.672 | 46.2506 | 31.4387 | 10.8131 | 14.8187 | 13.202 | 19.6596 | 37 | 6 | 8 | 2 | 46 | 31 | 10 | 14 | 13 | 19 | 168
44.3349 | 6.7733 | 8.8253 | 3.0109 | 64.6146 | 31.7892 | 10.4661 | 14.4611 | 15.5868 | 15.6361 | 44 | 6 | 8 | 3 | 64 | 31 | 10 | 14 | 15 | 15 | 191
49.7865 | 4.68 | 13.0469 | 2.9288 | 58.0966 | 26.6494 | 10.8305 | 13.5514 | 15.1518 | 15.8805 | 49 | 4 | 13 | 2 | 58 | 26 | 10 | 13 | 15 | 15 | 189
45.0348 | 6.3249 | 11.1057 | 3.5128 | 56.3484 | 31.0865 | 10.2635 | 16.198 | 13.7308 | 14.9957 | 45 | 6 | 11 | 3 | 56 | 31 | 10 | 16 | 13 | 14 | 186
32.9694 | 6.7213 | 10.3786 | 3.0245 | 46.5037 | 33.4395 | 9.2759 | 17.3044 | 13.5118 | 10.0643 | 32 | 6 | 10 | 3 | 46 | 33 | 9 | 17 | 13 | 10 | 161
34.6874 | 6.9768 | 9.6827 | 3.3035 | 60.3235 | 24.3149 | 10.07 | 16.1484 | 15.577 | 17.8779 | 34 | 6 | 9 | 3 | 60 | 24 | 10 | 16 | 15 | 17 | 175
51.8937 | 5.5633 | 12.7665 | 2.7775 | 62.8676 | 25.5985 | 11.7967 | 15.8167 | 15.251 | 16.0218 | 51 | 5 | 12 | 2 | 62 | 25 | 11 | 15 | 15 | 16 | 196
56.3125 | 5.7015 | 11.9712 | 2.7591 | 58.9803 | 29.8669 | 9.3797 | 14.7238 | 12.1881 | 13.9584 | 56 | 5 | 11 | 2 | 58 | 29 | 9 | 14 | 12 | 13 | 193
36.3042 | 6.1712 | 12.0221 | 2.3129 | 54.026 | 34.4226 | 9.2337 | 10.9169 | 14.7756 | 7.5866 | 36 | 6 | 12 | 2 | 54 | 34 | 9 | 10 | 14 | 7 | 167
37.9631 | 5.7201 | 11.8753 | 2.3946 | 60.242 | 29.2479 | 8.4536 | 16.4164 | 14.2068 | 18.3927 | 37 | 5 | 11 | 2 | 60 | 29 | 8 | 16 | 14 | 18 | 185
33.6588 | 5.6219 | 11.5056 | 3.3055 | 55.0157 | 21.9332 | 10.6492 | 14.4053 | 14.7972 | 10.5122 | 33 | 5 | 11 | 3 | 55 | 21 | 10 | 14 | 14 | 10 | 158
54.87 | 5.4895 | 13.0176 | 3.0136 | 65.1378 | 28.2457 | 11.5501 | 11.6092 | 13.8772 | 15.8546 | 54 | 5 | 13 | 3 | 65 | 28 | 11 | 11 | 13 | 15 | 199
45.9183 | 6.0514 | 9.5553 | 2.9184 | 66.9403 | 32.64 | 9.5584 | 16.192 | 13.9185 | 22.7981 | 45 | 6 | 9 | 2 | 66 | 32 | 9 | 16 | 13 | 22 | 203
49.7616 | 6.4227 | 10.9213 | 3.5118 | 59.4442 | 30.8016 | 9.976 | 15.6972 | 15.3507 | 11.5874 | 49 | 6 | 10 | 3 | 59 | 30 | 9 | 15 | 15 | 11 | 189
39.9294 | 5.4462 | 9.0503 | 3.4243 | 55.7747 | 29.0282 | 9.9548 | 17.2703 | 16.8729 | 19.9124 | 39 | 5 | 9 | 3 | 55 | 29 | 9 | 17 | 16 | 19 | 184
35.3696 | 6.336 | 9.985 | 3.4945 | 44.5017 | 32.7268 | 9.1319 | 13.0396 | 15.031 | 14.1795 | 35 | 6 | 9 | 3 | 44 | 32 | 9 | 13 | 15 | 14 | 162
58.22 | 5.5138 | 9.4381 | 3.0682 | 49.6214 | 30.7042 | 8.7894 | 16.4236 | 14.9667 | 15.0638 | 58 | 5 | 9 | 3 | 49 | 30 | 8 | 16 | 14 | 15 | 191
47.0063 | 6.9862 | 10.2742 | 2.6111 | 58.5668 | 27.8977 | 10.9268 | 19.3083 | 12.6255 | 23.9672 | 47 | 6 | 10 | 2 | 58 | 27 | 10 | 19 | 12 | 23 | 196
32.4408 | 5.9974 | 12.5735 | 2.7542 | 62.0253 | 30.9394 | 9.5413 | 16.3784 | 16.6323 | 12.3487 | 32 | 5 | 12 | 2 | 62 | 30 | 9 | 16 | 16 | 12 | 180
49.113 | 6.1428 | 10.0343 | 3.1418 | 55.4941 | 29.6438 | 10.6613 | 13.4787 | 12.6931 | 11.702 | 49 | 6 | 10 | 3 | 55 | 29 | 10 | 13 | 12 | 11 | 179
43.5321 | 6.2736 | 10.4112 | 2.7674 | 46.9997 | 29.6232 | 9.6008 | 17.9846 | 15.438 | 15.8567 | 43 | 6 | 10 | 2 | 46 | 29 | 9 | 17 | 15 | 15 | 175
52.136 | 5.7152 | 10.7746 | 3.3265 | 65.3321 | 34.1615 | 10.4592 | 16.9813 | 14.6057 | 6.0876 | 52 | 5 | 10 | 3 | 65 | 34 | 10 | 16 | 14 | 6 | 197
40.7078 | 6.5407 | 9.9011 | 3.3551 | 60.0076 | 33.3189 | 9.5047 | 16.135 | 15.1378 | 21.236 | 40 | 6 | 9 | 3 | 60 | 33 | 9 | 16 | 15 | 21 | 194
42.7127 | 6.118 | 12.2467 | 2.2912 | 59.503 | 33.0307 | 9.9234 | 13.6901 | 14.0662 | 20.0845 | 42 | 6 | 12 | 2 | 59 | 33 | 9 | 13 | 14 | 20 | 193
42.333 | 4.58 | 9.9658 | 3.0324 | 45.697 | 33.2536 | 9.3804 | 13.2731 | 13.9536 | 9.3612 | 42 | 4 | 9 | 3 | 45 | 33 | 9 | 13 | 13 | 9 | 164
46.6535 | 6.8643 | 10.3126 | 3.1536 | 74.6566 | 26.5986 | 9.5228 | 15.8784 | 14.8719 | 14.4022 | 46 | 6 | 10 | 3 | 74 | 26 | 9 | 15 | 14 | 14 | 199
45.3957 | 7.3803 | 8.0944 | 3.0824 | 65.3786 | 34.8179 | 11.3484 | 18.4183 | 14.6988 | 20.8794 | 45 | 7 | 8 | 3 | 65 | 34 | 11 | 18 | 14 | 20 | 204
43.2567 | 5.7225 | 10.7531 | 3.3319 | 58.1459 | 28.7648 | 9.6353 | 12.8636 | 16.0967 | 11.0212 | 43 | 5 | 10 | 3 | 58 | 28 | 9 | 12 | 16 | 11 | 178
48.6753 | 5.328 | 10.1599 | 2.9602 | 69.3846 | 29.5234 | 9.5617 | 13.9438 | 15.5584 | 19.2539 | 48 | 5 | 10 | 2 | 69 | 29 | 9 | 13 | 15 | 19 | 203
49.1535 | 6.9271 | 9.9219 | 3.2126 | 58.8691 | 25.0987 | 8.6447 | 16.6192 | 15.4124 | 21.1594 | 49 | 6 | 9 | 3 | 58 | 25 | 8 | 16 | 15 | 21 | 193
43.6576 | 6.3129 | 10.3467 | 2.954 | 68.309 | 28.3701 | 9.5679 | 15.3108 | 15.1324 | 19.9863 | 43 | 6 | 10 | 2 | 68 | 28 | 9 | 15 | 15 | 19 | 198
36.8161 | 6.4516 | 8.224 | 2.7497 | 65.4139 | 37.2234 | 10.2698 | 14.7536 | 14.4654 | 22.8459 | 36 | 6 | 8 | 2 | 65 | 37 | 10 | 14 | 14 | 22 | 196
45.6757 | 6.2508 | 11.3077 | 3.003 | 66.6192 | 37.042 | 9.5907 | 13.3765 | 15.9788 | 6.9589 | 45 | 6 | 11 | 3 | 66 | 37 | 9 | 13 | 15 | 6 | 193
35.724 | 7.5517 | 7.7763 | 2.5579 | 51.2064 | 33.0343 | 11.195 | 14.48 | 15.997 | 19.5885 | 35 | 7 | 7 | 2 | 51 | 33 | 11 | 14 | 15 | 19 | 174
53.1911 | 6.6548 | 7.7452 | 2.4385 | 74.8533 | 36.0199 | 11.53 | 14.8055 | 15.6477 | 14.2387 | 53 | 6 | 7 | 2 | 74 | 36 | 11 | 14 | 15 | 14 | 213
50.1371 | 6.3728 | 11.3792 | 3.0972 | 43.6661 | 24.4653 | 10.0775 | 15.7353 | 16.5246 | 15.5071 | 50 | 6 | 11 | 3 | 43 | 24 | 10 | 15 | 16 | 15 | 174
39.2222 | 7.0179 | 8.7523 | 2.8637 | 64.1573 | 25.3105 | 8.5853 | 17.4356 | 13.4155 | 5.9221 | 39 | 7 | 8 | 2 | 64 | 25 | 8 | 17 | 13 | 5 | 171
34.5275 | 5.4079 | 6.6429 | 2.8536 | 59.3508 | 35.2075 | 10.529 | 18.7742 | 14.7227 | 17.2685 | 34 | 5 | 6 | 2 | 59 | 35 | 10 | 18 | 14 | 17 | 183
43.8831 | 5.5487 | 8.5019 | 2.6219 | 57.9552 | 28.9707 | 10.0528 | 17.5806 | 15.1371 | 9.684 | 43 | 5 | 8 | 2 | 57 | 28 | 10 | 17 | 15 | 9 | 177
47.216 | 6.583 | 10.7121 | 3.0835 | 64.2624 | 38.4621 | 9.6888 | 12.242 | 15.7641 | 15.808 | 47 | 6 | 10 | 3 | 64 | 38 | 9 | 12 | 15 | 15 | 201
39.7362 | 7.9723 | 9.3374 | 2.418 | 52.1909 | 31.8583 | 10.9871 | 13.3537 | 16.8889 | 15.57 | 39 | 7 | 9 | 2 | 52 | 31 | 10 | 13 | 16 | 15 | 175
54.7025 | 5.8536 | 11.2941 | 2.788 | 71.3792 | 21.5493 | 9.6228 | 14.4354 | 17.4126 | 14.5631 | 54 | 5 | 11 | 2 | 71 | 21 | 9 | 14 | 17 | 14 | 202
43.6948 | 6.8822 | 9.7823 | 3.3206 | 60.692 | 32.1264 | 11.1431 | 15.9306 | 14.2135 | 11.3797 | 43 | 6 | 9 | 3 | 60 | 32 | 11 | 15 | 14 | 11 | 184
51.4338 | 6.5745 | 12.5502 | 3.2696 | 46.621 | 28.5155 | 9.2305 | 13.7823 | 17.2633 | 17.2981 | 51 | 6 | 12 | 3 | 46 | 28 | 9 | 13 | 17 | 17 | 184
39.3417 | 5.8643 | 10.1156 | 3.5236 | 53.3025 | 25.3991 | 10.2522 | 16.038 | 15.9453 | 18.9956 | 39 | 5 | 10 | 3 | 53 | 25 | 10 | 16 | 15 | 18 | 176
45.3311 | 6.0181 | 10.5857 | 3.2572 | 53.4318 | 28.6384 | 11.6474 | 14.8051 | 14.1634 | 10.3598 | 45 | 6 | 10 | 3 | 53 | 28 | 11 | 14 | 14 | 10 | 174
44.0429 | 6.1191 | 10.1457 | 3.8194 | 67.7762 | 32.5197 | 9.9194 | 15.1728 | 15.7244 | 8.5996 | 44 | 6 | 10 | 3 | 67 | 32 | 9 | 15 | 15 | 8 | 191
41.4093 | 5.3276 | 11.5713 | 3.063 | 54.6379 | 36.3021 | 10.7462 | 19.7099 | 14.0373 | 21.1586 | 41 | 5 | 11 | 3 | 54 | 36 | 10 | 19 | 14 | 21 | 196
51.3587 | 6.8725 | 11.1301 | 2.5484 | 76.9195 | 29.3409 | 11.4791 | 14.0719 | 14.1891 | 23.8256 | 51 | 6 | 11 | 2 | 76 | 29 | 11 | 14 | 14 | 23 | 218